## Budget Forcast Report
Delivery Management | No of Days | No Of Trips | No of Months | Costing In SGD Dollars | Budgetted Cost | Actual Budget | Comments
NUS extension work |  |  |  |  | 8500 | 8500 | This is T & M project with Fixed Budget duration is 1 month
Requirement Gathering and Designing (HLD)
Arpita | 15 |  |  | 495 |  |  | Assumption Arpita will be gathering the requirement with Customer and performing HLD design and training on BPM
Design, Coding and Unit testing | [6 empty] | Assumption Perdiem in SG is 25
Dev | 0 |  |  | 0 |  |  | Per Diem
Arpita (offshore) | 15 | [5 empty] | Aprita support for completing the project and guiding the Developer and Tester
Testing
Padmini | 5 | [5 empty] | Performing test case creation and execution
Travel Cost (Flight fares)
Arpita |  | 1 |  | 750 |  |  | Flight ticket from Bangalore to SG approx 35k INR
Dev |  | 0 |  | 0
Accomdations:
Hotel Stay in SG for Arpita | 15 |  |  | 2250 |  |  | I have assumption Fragance Hotel at SG cost 121 + 25 = S$ 150 /night | SGD Conversion | 48
Miscellanous | 20 |  |  | 450 |  |  | Mobile Internet, Local Transportation etc Approx S$ 500
Training and Material
Training and Material |  |  |  | 0
Salaries | [6 empty] | Ganesh Need to check on the Salary Component | Yearly | Monthly | Day
Arpita |  |  | 1 | 1736.1111 |  |  | Actual Salary is considered and calculated | 1000000 | 83333.3333 | 10416.6667
Dev |  |  | 1 | 1388.8889 |  |  | Actual Salary is considered and calculated | 800000 | 66666.6667 | 8333.3333
Padmini |  |  | 0.25 | 347.2222 |  |  | Actual Salary is considered and calculated | 800000 | 66666.6667 | 8333.3333
|  | Total |  | 7070
|  |  |  | 1414 | 20% | Margin
8484