## Budget Forcast Report
Budget and Cash Flow for Milestone --> To Be Architecture or Blue Print phase (Till 20 Apr 2015) And Development Phase (Till 7 Apr 2015)
Delivery Management | No of Days | No Of Trips | No of Months | Costing In Dollars | Budgetted Cost | Actual Budget | Comments
SLT - SOA & BPM - 30% Upon Blue Print Design Completion |  |  |  |  | 350000 | 105000 | Considered for To Be Architecture Workshop as 35% overall Budgetted Cost
Project Management
Krishnaraju | 122 |  |  | 3050 |  |  | Per Diem
As-is-Analysis
Business Process Analysis
Arpita | 85 |  |  | 2125 |  |  | Per Diem
Shailesh | 92 |  |  | 2300 |  |  | Per Diem
Poonam | 60 |  |  | 1500 |  |  | Per Diem
API information Capturing
Rajasekhar | 21 |  |  | 525 |  |  | Per Diem
Narendra | 10 |  |  | 250 |  |  | Per Diem
Annapurna | 58 |  |  | 1450 |  |  | Per Diem
Travel Cost (Flight fares) | [6 empty] | Per Diem
Krishnaraju |  | 8 |  | 4666.6667
Arpita |  | 9 |  | 5250
Rajasekhar |  | 1 |  | 583.3333
Shailesh |  | 5 |  | 2916.6667
Poonam |  | 3 |  | 1750
Narendra |  | 1 |  | 583.3333
Annapurna |  | 4 |  | 2333.3333
Harish |  | 5 |  | 2500 |  |  | Harish Need your input here I have taken approx number
Local transportation Expenses
Rajasekhar |  |  |  | 53.3333 |  |  | Local transportation in India and SriLanka
Arpita |  |  |  | 400 |  |  | Local transportation in India and SriLanka
Krishnaraju |  |  |  | 600 |  |  | Local transportation in India and SriLanka
Shailesh |  |  |  | 300 |  |  | Local transportation in India and SriLanka
Poonam |  |  |  | 300 |  |  | Local transportation in India and SriLanka
Annapurna |  |  |  | 300 |  |  | Local transportation in India and SriLanka
Narendra |  |  |  | 50 |  |  | Local transportation in India and SriLanka
Harish |  |  |  | 500 |  |  | Local transportation in Singapore and SriLanka
Accomdations:
Apt 6/2B (Including electricity and Water Bills) |  |  | 5 | 15000 |  |  | Sept,Oct,Nov,Dec
Apt 5/4B (including electricity and water Bills) |  |  | 3 | 9000 |  |  | Nov, Dec
Apt 7/2b (including Bills) |  |  | 0.25 | 1100 |  |  | Nov 1 week
Miscellanous |  |  |  | 3000 |  |  | Mobile Internet, Apt Cleaning, Team Lunch
Hilton Hotel (krishnaraju) | 1 |  |  | 150
Hilton Hotel (Harish) | 5 |  |  | 875
Cinnamon Red (krishnaraju) | 2 |  |  | 300 |  |  | Recent travel to colombo -- 6- 8 Apr 2015
Cinnamon Red (Arpita) | 12 |  |  | 1650 |  |  | Recent travel to colombo -- 15-27 Apr 2015 for 11 nights
Salaries | [6 empty] | Ganesh Need to check on the Salary Component | Yearly | Monthly | Day
Krishnaraju |  |  | 6 | 15533.3333 |  |  | Actual Salary is considered and calculated | 1864000 | 155333.3333 | 19416.6667
Arpita |  |  | 6 | 8908.3333 |  |  | Actual Salary is considered and calculated | 1069000 | 89083.3333 | 11135.4167
Shailesh |  |  | 5 | 15604.1667 |  |  | Actual Salary is considered and calculated | 2247000 | 187250 | 23406.25
Poonam |  |  | 3 | 9362.5 |  |  | Actual Salary is considered and calculated | 2247001 | 187250.0833 | 23406.2604
Rajasekhar |  |  | 3 | 2779.1667 |  |  | Actual Salary is considered and calculated | 667000 | 55583.3333 | 6947.9167
Prahlad |  |  | 2 | 1852.7778 |  |  | Actual Salary is considered and calculated | 667000 | 55583.3333 | 6947.9167
kavin |  |  | 2 | 7177.7778 |  |  | Actual Salary is considered and calculated | 2584000 | 215333.3333 | 26916.6667
Tony |  |  | 0.25 | 1092.3611 |  |  | Actual Salary is considered and calculated | 3146000 | 262166.6667 | 32770.8333
Narendra |  |  | 0.75 | 3277.0833 |  |  | Actual Salary is considered and calculated | 3146001 | 262166.75 | 32770.8438
Annapurna |  |  | 4 | 17477.7778 |  |  | Actual Salary is considered and calculated | 3146002 | 262166.8333 | 32770.8542
Rajesh |  |  | 0.5 | 2184.7229 |  |  | Actual Salary is considered and calculated | 3146002 | 262166.8333 | 32770.8542
|  | Total |  | 148426.9444
|  | Cost Difference after BP phase |  | -43426.9444