## Chronological Evidence summary
Sl No | Events | Date | Event Description | Email Subject | Email Description
SOA platform installation
1 | SOA Platform Readiness | 2015-01-16 | SOA Platform Readiness | SOA Platform Readiness | Entire Development environment was up and running and performed the validation of process by deploying the sample process use case to see the integrationw ith BPM and IIB.
Current state Analysis
1 | Detail scoping workshop activity on the core process started | 2014-04-09 | Detail scoping workshop activity on the core process started | Detail scoping workshop activity on the core process started | Due to inexperience from Nable team, we had heated agrument of not capturing the existing core process functionality properly.
2 | Capturing of core process AS-is-models. | 2014-12-12 | Capturing of core process AS-is-models. | Capturing of core process AS-is-models. | It took more then initatial planned for 5days due to lack of understanding from Nable team and every interactions we had several discussion to bring it closure.That leads time tooks to bring every one into common page and got the sign off from customer.
| Capturing of Extended process AS-is-models | 2015-01-01 | Capturing of Extended process AS-is-models | Capturing of Extended process AS-is-models | Capture of the extended process starting in mid of novemember, however while capturing the business exception along with extended process got delayed and also found that SLT was delaying in the providing the information.
Design Phase
1 | Design Phase for BPM and IIB | 2014-06-02 | Design Phase for BPM and IIB | Design Phase for BPM and IIB | We have followed the Iterative approach, while performing the design in BWL, we have used the same BWL flows in to the process designer and performed the coding in parallel
Scott Involvement to SLT Project
1 | Workshop activity at SLT | 24/10/2014 | First Day of Workshop activity | Scott send out the email due to tax constraints he could not travel | First day episode was managed by the Ajith and entire SLT CIO was attended and provided the speech for successful start of workshop activity. At the end of the workshop, Rohitha and Naleen commented not having the IBM presence in the workshop and brought into complete workshop to Halt.
2 | Workshop activity at SLT | 28/10/2014 | Sec Day of workshop activity | Due to non availability of IBM smarter CoC, SLT has requested to cover other than process model flows | Ajith has covered the governance part as a part of workshop activity.
3 | Workshop activity at SLT | 24/11/2014 | First Day of Workshop activity | Scott availability was confirmed his availability after having the 9 weeks of delay in workshop activity | Scott availability was confirmed after successive delay of 9 weeks and at last 24 Nov 2014 second round of workshop activity has happened.
4 | Blue print submission | 2015-01-01 | First Final Version of Blue print with Etom Aligned process models was submitted to SLT | After having 5 times of walk through the Blue print document and finally we have submitted the Blueprint for sign off with SLT | After having 5 times of walk through the Blue print document and finally we have submitted the Blueprint for sign off with SLT. SLT has requested for IBM to sign off on this documentation.
5 | Scott availability for performing the reviewer on Blueprint and Etom Aligned process models. | 17/1/2015 | Had a discussion with IBM team | Intense discussion with IBM team and got the availability of scott to perform the review | Intense discussion and agrument we had with IBM and IBM finally agreed to provide the scott availability in a capacity as reviewer in the documentation and his review comments will be incorporated and shared for Blue print signoff
6 | Scott shared the review comments | 2015-01-02 | Review comments from Scott was shared with the team | Review comment was shared to the team | Ajith, Prasad, Amila and Aprita has updated accordingly Blueprint and Etom Aligned process model for the SLT sign off.
7 | Offical Blue print was signed off on 2 Feb | 2015-02-02 | Offical Blue print was signed off on 2 Feb | Offical Blue print was signed off on 2 Feb | Offical Blue print was signed off on 2 Feb, however SLT wanted to TAM Map alignment and Business Exception documentation to be completed. SLT has taken other direction for not signing the Etom Aligned document and raised that ETOM alignment is not done properly. SLT raised concerns on the scott should be available and explaing the ETOM alignment clarification session. SLT wanted to have scott to perform the clarification workshop for Etom Alignment
8 | Design document was shared for Scott review | 2015-10-03 | Design document was shared for Scott review | Design document was shared for Scott review | Design document was shared with Scott to perform the review, however no reply from the scott.
Marliza Involvement to SLT Project
1 | Monthly Meeting with IBM | 2015-02-03 | 1) Project Status update. 2) Addressing the pain points 3) Escalation on the delay with IBM involvement and Telco Pack | IBM Smarter Process CoC involvement in SLT SOA/BPM project | Hi OIe, As discussed day before yesterday, let get into a conference call today at 2:30 SL time (GMT+5:30) to finalize on the scope of the CoC and see the mechanism of engaging your team on the to-be workshop (which is to be scheduled next week or week after). Our expectation from your team is as follows; 1. Advisory support in planning for the To-be workshop 2. Taking part in the To-be workshop and direct it in line with best practices of IBM in order to design of the To-be architecture 3. Review and validate the Blue-Print design for 4. Mentoring session for SLT/i2S and N-able on the use of IBM Telecom Pack before the design and development of the in-scope processes (core-processes - please see the SOW attached herewith) 5. Assist the design, modeling and development of one (1) end-to-end process (in-scope core processes) 6. Assist the design, modeling and development of one (1) end-to-end process (in-scope extended processes) 7. Review and validate the design document for in-scope processes 8. Review and validate the final build of the end-to-end in-scope processes (five) in view of ensuring it is in line with IBM best practices 9. Indicate the best practice guidelines for business process documentation for SLT I have attached the SOW for i2S which has the definitions used above, tks. _______________ Prasad Kularatne Principal Consultant N-Able (Pvt.) Limited D: 94 114 625010 M: 94 727 684770
2 | Reply from Vincent Baruchello from IBM | 2015-03-02 | Scott Availability for Telco Pack Training | Re: Fwd: IBM Smarter Process CoC involvement in SLT SOA/BPM project [*URGENT*] | Hi All, Glad to hear the good news, and sorry about our challenges. While waiting for Scott's next ability to travel to Sri Lanka, if you need an immediate action, I can offer some assistance for this week and probably next with Sila (in Cc). Sila is based in the US and he is knowledgeable with the Telco Pack. He is waiting for a visa to work in Africa, so this week and potentially next, he should be available. Not sure how practical this is and if we can leverage this option in the meantime. Let me know. Thanks, Regards ________________________________________ Vincent Baruchello 17 avenue de l'Europe WW Leader Bois Colombes, Cedex 92275 Global Business Services Smarter Process Center of Competence France Phone: +33 1 58 75 38 80 Mobile: +33 6 68 07 91 89 e-mail: baruchello@fr.ibm.com
3 | Marliza has sent email to Arpita for BWL information | 2015-03-12 | Requesting for the access to BWL information | RE: SLT SOA Project : Process Models, SID objects & Services related information | Arpita, during our last call you mentioned that you were going to send us the SLT Design Document and the link/access to BWL, so far we have not received anything from you. Could you please send the information ASAP. We are planning a visit to SLT and it's important to have this information. Thanks Cheers, Marilza Maia IBM Sr. Certified IT Specialist IBM Software Group - Industry Solution Services San Francisco, CA mmaia@us.ibm.com 510-654-1858 Mobile Office
4 | Arpita reply to Can Paul and Marliza | 2015-03-12 | Requesting Arpita to provided the detaled information on Prcesses captured in BWL | SLT SOA Project : Process Models, SID objects & Services related information | Dear Can/Marilza, Please find below the information we agreed to share towards the end of the call yesterday. Sorry about the delay. Process Models Unfortunately, the account used has limitations on the number of users. So, please use the below credentials to look up the updated flows. Username: dishagi@n-able.biz Password: sltbpr11 The latest process models are in the space “Updated To Be Process models_09_02_15”. The main processes are as follows. • OrderHandling_Create_V0.7 (for new connections) • OrderHandling_Modify_V0.7 (for changes) • OrderHandling_Suspend_V0.7 (for suspending services temporarily) • OrderHandling_Resume_V0.7 (for resuming temporarily suspended services) • OrderHandling_Delete_V0.7 (for terminating the services) • OrderHandling_Cancel_V0.7 (for cancelling an in-progress order) • OrderHandling_ExtendedModifications_V0.7 (for relocations) SID Objects The SID objects we are using from the Telco Pack are as follows: • CustomerOrder • ServiceOrder • Product • ProductOrder • SiteAddress We have added parameters in the Extensions of these objects as per the requirements from SLT back-end APIs. Services The services being exposed from/to IIB are as follows: 1. Create Contract 2. Create Contact Point 3. Check if address exists 4. Create Address 5. Attach Address to Customer ID 6. Create customer in billing system 7. Create Account in OSS 8. Create Account in billing system 9. Determine Service Parameter Availability 10. Reserve Service Parameters 11. Allocate Service Parameters 12. Create Service Orders 13. Provision Service Orders 14. Monitor Service Order Status 15. Issue Service Orders 16. Close Service Order 17. Wait for back-end system to inform when milestone is reached 18. Get the attributes of the Service Order from back-end 19. Get the features of the Service Order from back-end 20. Update the Service Order status information in CRM 21. Wait for back-end system to inform when service is provisioned 22. Wait for back-end system to inform when service is suspended 23. Wait for back-end system to inform when service is reactivated 24. Wait for back-end system to inform when service is deactivated 25. Cancel Service Orders 26. Wait for back-end system to inform when service is cancelled 27. Send Request for Approval/Validation 28. Wait for Approval/Validation Response 29. Update BSS Products 30. Create billing products 31. Activate billing products 32. Update billing products 33. Suspend billing products 34. Resume billing products 35. Deactivate billing products Warm Regards, Arpita Roy Practice Lead (WebSphere Technologies) i2s Business Solutions India Pvt Ltd No:3421, 10th Main 3rd cross, 100 Feet Road, Indira Nagar II stage, Bangalore –560038. Mobile: +91-9008555443 (India), +94-765248219 (Sri Lanka) www.i2sbs.com
5 | Reply from Prasad | 2015-03-13 | Requesting for Donald find for alternative to Scott Availability for TC training | Re: Fwd: IBM Smarter Process CoC involvement in SLT SOA/BPM project [*URGENT*] | Hi Don, There are different discussions on the availability of the resources. Scott Glen: who understands this project the most is unavailable due to other commitments Can-Paul: who did the initial intro to telecom pack and also had discussions to understand the current challenges of the project and this discussion is to be continued. Team member from Michael O Sauro: Most probably may not have exposure to the project at SLT Based on the availability, I understand that one of them will come. However, I suggest that resource gets an understanding of the immediate needs of SLT. 1. Telecom Pack mentoring with special reference to accelerating the design & development phase of the project 2. Recommending an approach for order decomposition in the BPM layer. What assistance IBM can provide in building the order decomposition in the suggested approach. Note: On this currently Scott offered to help remotely at his spare time. He is analyzing the customer's OSS API's. Hence the if the resource you plan is required to be knowledgeable of the work already done. Thanks.
6 | Email from Prasad to Can Paul and Scott | 2015-03-13 | Sharing the BP document to Can Paul and Scott | Re: Fwd: IBM Smarter Process CoC involvement in SLT SOA/BPM project [*URGENT*] | Hi Scott/Can-Paul, I have attached the design/development activities that we have carried out post to Blue Print stage. Tasks from process modeling (done in BWL) and rest of the activities done in PD, I've listed including the approach team has taken. To address our request to help in accelerating the project activities (mainly using telecom pack assets), you can base your recommendations based on what we've carried out thus far. I've copied Arpita, how is the technical project lead and Ajith who is the telecom architect for the SLT SOA/BPM project.
7 | Can Paul email to Prasad | 2015-03-13 | Sharing the Marliza is the candidate with lots of experience in Telco Pack | Re: Fwd: IBM Smarter Process CoC involvement in SLT SOA/BPM project [*URGENT*] | Just one clarification. I work for Mike Sauro and so does Marilza. We have both been on all the calls with stl/nable, and based on availability and your immediate need Marilza will come out on site as soon as possible. She has already been doing background discovery and now diving into what n-able sent us in the last few days. Marilza has been on our team for more than 5 years and has ample skills to help do the enablement. In addition she is a B10 skilled Architect with both implementation and sales background in bpm, modeler, odm. You will be in good hands. In parallel we will both continue working with you offshore until she can get the dou/sow/visa etc set up so she can be onshore. Regards, Can Paul Senior IT Architect Systems Group - Business Services Solutions Worldwide. (Telecoms, Media, Banking and Healthcare) can@us.ibm.com +1 410-212-2700
8 | Marliza requested for the call to discussion the SLT project | 2015-03-13 | Requesting for the conferenca call | SLT SOA Project : Process Models, SID objects & Services related information | I'm available for the call on Monday at 7:30 PM ET. Cheers, Marilza Maia IBM Sr. Certified IT Specialist IBM Software Group - Industry Solution Services San Francisco, CA mmaia@us.ibm.com 510-654-1858 Mobile Office
9 | Andrew Larmour | 2015-03-16 | Marliza travel discussion and VISA information | Re: Meeting with the SLT team from India | Hi Mariliza, You might want to double check on the visa on arrival, it may be different for US passport holders, but it is not possible for me to get a business visa on arrival at CMB and I had to get a visa from the LK consulate before departing MEL. Regards Andrew Larmour Chief Telecom Architect IBM Systems Unit IBM Worldwide Phone +61 (0*) 3 9626-6108 Mobile +61 (0*) 401 991-493 (* do not dial 0 if calling from outside Australia) Blog TelcoTalk Non-IBMers can now contact me via Sametime - just click here On 16 Mar 2015, at 3:25 pm, Madhava Siriwardhane <madhava@lk.ibm.com> wrote: Hi Marilza, I'm looping Prasad from N-able and IBM team so all are in the same page. Best Regards, Madhava. Sent from IBM Notes Traveler Marilza Maia --- Meeting with the SLT team from India ---
10 | Marliza reply to Andrew email | 2018-03-16 | Marliza reply to Andrew email | Re: Meeting with the SLT team from India | Hello Andrew, I did check it with CIBT and United airlines. They both asked me If I held a US passport, which I do. I can contact the SL Embassy, but as I understand it's okay. Cheers, Marilza Maia IBM Sr. Certified IT Specialist IBM Software Group - Industry Solution Services San Francisco, CA mmaia@us.ibm.com 510-654-1858 Mobile Office
11 | Email from Dishagi for attending TC session from 23-27 | 2015-03-18 | Dishagi email to Krishna on heads up of TC session | 23-27 Mar - Presence of IBM | Dear Krishna, With reference to the conversation Prasad have had with IBM, we could expect the presence in SL of Marilza Maia (IBM US), week starting from 23rd till 27th Mar. She basically would enlighten us and train us the appropriate use of Telco pack for SLT SOA project and thereby it could accelerate our development activities too. Therefore, would like to inform you to plan your team’s travel for next week here to carry out an effective sessions with them Thanks & Best Regards, Dishagi Ratnapriya N-Able (Pvt) Ltd ¦(+94)773 16 99 73
12 | Prasad Email to Dishagi and Arpita | 2015-03-18 | Prasad Email to Dishagi and Arpita | Re: 23-27 Mar - Presence of IBM | Looping Arpita. She comes from the team that develops Telecom Pack assets and I think she has a fair bit of understanding of what we've done already. I understand that there was a call last Sunday as well. Let's make use of this opportunity to effectively use Telecom Pack and speed up our remaining development tasks. She will also help us in identifying an approach for order decomposition and discuss the same with the customer, tks.
13 | Arpita forward the email from Scott to krishna and Sujith | 2015-03-18 | Arpita forward the email from Scott to krishna and Sujith | FW: Draft [Scott's mail on Telco Pack] | Hi, I have highlighted the Telco Pack related information. Please note that we used the data from the Telco Pack. However, we didn’t use the implementation services directly from the Telco Pack because - 1. We didn’t have enough idea on how to use the services from the TP with our ESB on IIB; 2. We were running short of time and the process models were not finalized; so the only sensible way to not delay the timelines any further was to develop the implementation services (which were fixed because the because the back-end APIs were not going to be changed) first using the data from the TP. We followed the same way. Once the process models were finalized, we imported the same into PD and used these implementation services. Warm Regards, Arpita Roy Practice Lead (WebSphere Technologies) i2s Business Solutions India Pvt Ltd No:3421, 10th Main 3rd cross, 100 Feet Road, Indira Nagar II stage, Bangalore –560038. Mobile: +91-9008555443 (India), +94-765248219 (Sri Lanka) www.i2sbs.com ---------- Forwarded message ---------- From: Scott Glen <scott.glen@uk.ibm.com> Date: Thu, Dec 4, 2014 at 12:32 AM Subject: RE: Draft To: Arpita Roy <arpita@i2sbs.com> Cc: Ajith Kumar <ajith@knowesis.com>, Krishnaraju <krishnaraju@i2sbs.com>, Prasad Kularatna <prasad@n-able.biz> a) its 7:30pm in Denmark ... must be 12 midnight in SL .. so ..... GO TO BED :o)) b) yes - I personally would NOT use the Order Handling sample from the TP. I think our BWL makes more sense (certainly from a data usage perspective) and hence when we develop models in PD I think they will be better. We still use the data and integration services from the pack. If you followed what I said in the last mail, the yes - lets use CO as input, embed the PO, decompose, issue 3 type of order, track 3 types of order, tidy up.... done. Sorry its taken a few days to get back to you ... arrived home on Sunday at 1am... and was in Ireland (Dublin) by 10 am Monday ... and now in Denmark ... so finally getting time to catch up. :o) By the way - I've travelling continuously over the last ten years - Europe, Africa, Middle East, Asia, US.... too many countries too remember ... but the team in SL were one of the most friendly and welcoming I have met. Many thanks to all. Cheers, Scott. ---------------------------------------------------------------------------------------------------------- Scott Glen, MBCS CITP CEng EMEA Lead Architect GBS-SWG Smarter Process Centre of Competence Software Group, IBM United Kingdom Limited IBM Certified IT Architect IBM Certified SOA Solution Designer Open Group Certified Master IT Architect office mobile: +44 (0)7894 393695 From: "Arpita Roy" <arpita@i2sbs.com> To: Scott Glen/UK/IBM@IBMGB Cc: "'Ajith Kumar'" <ajith@knowesis.com>, "'Krishnaraju'" <krishnaraju@i2sbs.com>, "'Prasad Kularatna'" <prasad@n-able.biz> Date: 03/12/2014 19:34 Subject: RE: Draft ________________________________________ Hey Scott, Thanks for your reply. I had one more query. Do you think it might be a good idea to discard the high level TP Order Handling flow entirely and instead use the one we have created in BWL. And then map the underlying implementation services to those in the TP? In that case we can also continue using the same data model as initially planned (with CO). As for BWL models, I can still see the different Track&Manage sections in them. I have attached the models here so that you can glance through them when you find time. Hi Ajith, I think we shared your BWL space with Scott; so maybe the changes are not there in that space. Can you please archive the existing models and import the ones attached? Warm Regards, Arpita Mobile : +94 765248219 (Sri Lanka), +91 9008555443 (India)
14 | Sujith email to Prasad | 2015-03-18 | Sujith email to Prasad | Re: 23-27 Mar - Presence of IBM | Hi Prasad, As per the current status we have completed substantial development activities and are planning towards start of SIT. As of today we are almost close to completion of Development activity and we have used Telco Pack as suggested by Scott. We have waiting for Telco pack session from January timeframe, which would have greater advantage to expedite or accelerate development phase. No doubt having the telco pack session will definite enhance the knowledge within the team and also if possible we could use or apply for remaining process which is at discussion with SLT. I am bringing or highlighting this point just to ensure that we don’t end up reworking on what has been accomplished by the team. I appreciate and recommend, Marilza to have a deep dive to SLT project and understand the requirements and development performed by the team till date and come out with recommendation on use of telco pack where ever needed. We could effective have Marilza time to perform review on Design and also take her suggestion on telco pack on the remaining scenarios like relocation, delete and cancel processes. I am basically avoiding any rework on completed development till date at this stage of the project. As requested, I feel Arpita will be ideal resource to provide and bring Marilza to have good understanding of process and services developed from the SOA Team. I have discussed with Arpita, she will be available for Telco pack session from 23 to 27 March 2015. I hope this plan should be in-line with the time line we are approaching the SLT SOA Project. Thank you Regards, Sujith Unnikrishnan i2s Enterprise Solutions Sdn Bhd 5.11 & 7.11, Level 5 & 7, 1 Technology Park, No 7, Tanjung Bandar Utama, Bandar Utama, 47800, Petaling Jaya, Selangor – Malaysia www.i2sbs.com, Cell: +60-16-3872025 From: Prasad Kularatne <prasad@n-able.biz> Date: Wed, 18 Mar 2015 12:40:01 +0530 To: Dishagi Ratnapriya <dishagi@n-able.biz>, Arpita Roy <arpita@i2sbs.com> Cc: Krishnaraju <krishnaraju@i2sbs.com>, Shirley Nanayakkara <shirley@n-able.biz>, Suneth Kariyawasam <suneth@n-able.biz>, Amila Hendahewa <amila@n-able.biz>, Pirasanth Paramanathan <pirasanth@n-able.biz>, Sujith Unnikrishnan <sujith@i2sbs.com> Subject: Re: 23-27 Mar - Presence of IBM Looping Arpita. She comes from the team that develops Telecom Pack assets and I think she has a fair bit of understanding of what we've done already. I understand that there was a call last Sunday as well. Let's make use of this opportunity to effectively use Telecom Pack and speed up our remaining development tasks. She will also help us in identifying an approach for order decomposition and discuss the same with the customer, tks. On Wed, Mar 18, 2015 at 8:54 AM, Dishagi Ratnapriya <dishagi@n-able.biz> wrote: Dear Krishna, With reference to the conversation Prasad have had with IBM, we could expect the presence in SL of Marilza Maia (IBM US), week starting from 23rd till 27th Mar. She basically would enlighten us and train us the appropriate use of Telco pack for SLT SOA project and thereby it could accelerate our development activities too. Therefore, would like to inform you to plan your team’s travel for next week here to carry out an effective sessions with them Thanks & Best Regards, Dishagi Ratnapriya N-Able (Pvt) Ltd ¦(+94)773 16 99 73
15 | Reply from Prasad | 2015-03-19 | Reply from Prasad on Sujith email | Re: 23-27 Mar - Presence of IBM | Hi Sujith, Thanks for your mail and agreement to retain Arpita during the week starting from 23rd for this activity. In line with your requirements, please see the scope this IBM US resource will be delivering; • Walk through on the current Design Approach • Review existing process flows developed in Blue Works Live (BWL) • Ensure process are based on the TMF Frameworkx 12.5 and 13 • Ensure TMF Information Framework is used as the information model and the basis for application integration • Review recommended best practice approaches for Extending the Business Services and reusing the Telecom Pack Common Messaging Model In addition, I've requested her to look into the order decomposition concern and give us some recommendation. She indicated that it would need more time and perhaps will get an initial understanding during this visit and use some remote work hours to help us with that, tks.
16 | Prasad reply on the Marliza travel and content | 2015-03-19 | Prasad reply | Re: 23-27 Mar - Presence of IBM | Hi Krishna, Thanks for your views. Marilza is new to the environment. She would need to understand the approach taken and how we have come thus far. Therefore she needs to spend this first day in understanding what and how we've done and whether what we've done has resulted in the desired outcome for the project. Without this she would not be able to help us with possible improvements. For effective use of telecom pack to achieve the required acceleration, we should have followed a particular methodology, which I think is what Arpita and Ajith has come up with. She will just go through it and if needed would suggest improvements. Objectives are; 1. Her review will help us to validate what we've done will get us to the desired objectives as stipulated in the project scope. If there is anything we've missed or overlooked, it is better to know it now than realizing it during testing phase which would be costly. For example if our design and development is not inline with performance best practices, they we've fail performance tests and would have to go back and re-work. It is better to know of such issues in advance. 2. How the developers can effectively use telecom pack to speed up subsequent developments. Today our developers are not using telecom pack at all and it is supposed to provide acceleration. Thanks.
17 | TC walk thtough from Marliza | 2015-03-25 | TC walk thtough from Marliza | WebEx meeting scheduled: Telco Pack Walk through from Marilza | Hi, krishnaraju Manjrabad, You are the host for this WebEx meeting. Host key: 588946 (Use this to reclaim host privileges.) Telco Pack Walk through from Marilza Wednesday, March 25, 2015 10:00 am ¦ India Time (Mumbai, GMT+05:30) ¦ 3 hrs Join WebEx meeting Meeting number: 869 776 852 Meeting password: meeting2 Join by phone Conference Bridge Details: +1 (605) 781-0005 Participant Access Code: 164179
18 | Day 4 Walk through the TC session | 2015-03-28 | MOM reply on Prasad Intrepretation | Re: IBM Consulting for SLT SOA/BPM project - Day4 | Hi all, Today's session was intended at walking the team through the SID data mapping exercise. We understood the importance of doing this exercise with the BSS vendor as the data mapping requires a deeper understanding of the the fields/elements for each back-end operation we will be using within our scope. I thought it was a very effective day for the team as they could really see the real acceleration provided by Telecom Pack. By copy Arpita, please update, add any points I might have missed. 1. Telecom Pack version: Importance of correct up-to-date Telecom Pack version was highlighted. Since we had used an older version of telecom pack, the data mapping we've already done in incomplete and the exercise should be carried out again. Marilza recommended us to use Telecom Pack v7.5.0.0 with iFix JR51530 Note: At this point, I feel that we should involve BSS vendor in this exercise and since we have to carry out the data mapping activity again, my suggestion is that we go ahead with the latest BSS system API's, this will allow us to get more support from the vendor which we is lacking at the moment. 2. SID data mapping exercise: Marilza demonstrated how SID data mapping exercise should be carried out with the use of Telecom Pack assets. It was basically a top-down approach. Once our implementable flows are finalized, we can map API calls invoked at each task to the TAM operations defined in Telecom Pack. Marilza also explained how the data mapping can be carried out and the need to update the extensions in the SID objects inside PD. Once this exercise is carried out, we can import the TAM operation into IIB which in tern will create the appropriate Integration Service. Once the Integration service is created in IIB, we can build the message flows to do the native-to-SID transformations. Suneth felt this methodology can potentially accelerate the data mapping exercise at least 2-3 times compared to the approach he took initially. 3. Process flow design review: Marilza indicated that importance of having separate process flows from ground up for Move, Add, Change, Delete (MAC-D) scenarios as each such business process is different. She also mentioned that when we model such process flows they should be sufficiently generic to handle orders for different types of products. Arpita agreed to get her expert advice on improving the flows. 5. Involvement of the Solution Architect: Marilza indicated that it would be important for Solution Architect to involve more in the design and development to drive the architectural decisions. More involved decisions relating to externalizing of decisions within process flow into ODM and determination of composite vs. atomic services were some of the areas Marilza thinks the Solution Architects involvement is required. 6. Level of detail required in Process Flows: Marilza's review indicated that the process models when passed on to the developers from the BA would required to be at a more detailed level. She suggested to always look into breaking the processes all the way down to eTOM level-5 as much as possible. More details on the input/output messages points at which we externalized decisions into ODM and detailed contextual documentation were recommended to be included in the process models once they are broken down into much more details level where possible. 7. Developers role: Marilza highlighted the importance of developers role in BPM development. They should question the BA and architect to drill down and understand the process flow better before starting their development. Thanks. On Wed, Mar 25, 2015 at 7:34 AM, <arpita@i2sbs.com> wrote: Hi all, Please find the updates on some of the points inline. Warm Regards, Arpita Roy Practice Lead (WebSphere Technologies) i2s Business Solutions India Pvt Ltd No:3421, 10th Main 3rd cross, 100 Feet Road, Indira Nagar II stage, Bangalore –560038. Mobile: +91-9008555443 (India), +94-765248219 (Sri Lanka) www.i2sbs.com From: Prasad Kularatne [mailto:prasad@n-able.biz] Sent: Wednesday, March 25, 2015 3:32 AM To: Arpita Roy Cc: Amila Hendahewa; Suneth Kariyawasam; Shirley Nanayakkara; Marilza Maia; Can P Boyacigiller; Ajith Kumar; Scott Glen; Dishagi Ratnapriya; Krishnaraju Subject: Re: IBM Consulting for SLT SOA/BPM project - Day2 Hi all, Today's session started off with the installation of Telecom Pack assets on an SOA team members laptop to be used in the remaining part of the consulting engagement. By copy Arpita, please update, add any points I might have missed. 1. Marilza demonstrated how to resolve the dependency conflicts that arose when we started installing all the toolkits that comes with Telecom Pack 7.5.0.0 iFix JR48588. Finally we managed to have this version of telecom pack assets loaded into Shirley's laptop into a Process Center environment at N-able. 2. [arpita@i2sbs.com] We used one of smaller sub-processes “Track Service Provisioning Activity” inside the “Track & Manage Orders” sub-process from the “Extended Modifications” flow. This sub-process has one callback (which Marilza considers as a notification), 2 notification tasks and only one activity (Manage Customer Billing) which has 4 API calls to backend billing system. We used "Extended Modification" flow to understand the use of Telecom pack and how it will help us to accelerate our development. We used "Manage Customer Billing" activity within the process flow and started modeling it using Telecom Pack assets. 3. [arpita@i2sbs.com] We did not map our operations to TAM Applications and Operations, rather we only found from the Telco Pack Service Model (an excel sheet which comes with the ifix) the appropriate Telco Pack operation corresponding to our operation so that we can find the input and output of these operations. Currently, in the TP service model related resource interfaces (which contain these operations) are clubbed together and mapped to a particular TAM application. Using "Manage Customer Billing" as an example, Marilza demonstrated how to use BPM Telecom Pack. She demonstrated the need to understand the TAM Service Interfaces that contain "TAM Operations" we execute against the target systems within the activity. Within the above activity, we modeled a sub-flow and we found four operations to be executed against the BSS system and started mapping those to TAM Operations. She demonstrated how to import such operations in PD from the appropriate Telecom Pack toolkit and how we get the input and output message structures automatically in PD. 4. [arpita@i2sbs.com] Suneth/Shirley highlighted how when this exercise was being done originally they could not complete the allocated tasks (to get the descriptions of all the elements in the requests and responses of the API operations) because when they spoke to the SLT team they were unaware of the descriptions of the elements. Prasad suggested that we take up this work again with the BSS vendor to see if they know the appropriate descriptions. Once the Operations were mapped, we started the exercise of data mapping. As a preparation for that all relevant operations and elements of those operations were imported into an Excel sheet. During this exercise, we found certain elements in the SLT BSS operations were very specific to SLT BSS system and there was inadequate documentation (only Java doc) available to understand the use of these elements. Suneth/Shirley felt the need to work with BSS vendor team during the data mapping exercise to have a better understanding of these elements and therefore carry out the correct mapping into the SID data model. 5. There was a concern by the SOA team that during the data mapping, there were lots of elements that we could not map to a corresponding SID element and we therefore treated them as extensions. Marilza found out that we were using specific toolkits from a version of Telecom pack older than the one comes with iFix JR48588, and the organization of the Business Objects in that version was different to the one that comes with iFix JR48588. Taking "Customer Order" business object, she showed how different the organization of elements in the older version we were using and the one that comes with JR48588. This may be one of the reasons SOA team data mapping exercise resulted in a significant number of SID extensions. With the JR48588 toolkits, due to the hierarchical organization of related business objects, the mapping exercise would have been much easier and the team could have found the relevant entities easier. 6. Marilza indicated that she will get the latest recommended iFix version for the use in this project. On the third day we expect Marilza to help us in SID data mapping exercise and now that we have Operations from SLT BSS system with their elements and the relevant SID entities in Excel format, we can start the mapping activity from the morning with i2S team also connected via WebEx. We also plan to meet SLT, the Siebel project team, to understand how the order handling will happen with the new CRM implementation. The objective of this discussion is to understand how we should carry out order decomposition and issuing the RFS order to SLT OSS system. Currently what we've agreed with SLT was that we will use an external Stub Service to do the mapping (we will hard-code the required CFS to RFS mapping) however, we have not started analysis of their service order messages going to OSS or BSS yet. [arpita@i2sbs.com] Again, we are not going to do any mapping from CFS to RFS in the stub service. The stub service will have the hard-coded decomposition for each products(not CFS). Practically, because this will be a hard-coded response, it will be exactly for a given products, irrespective of what CFS are being passed. On Tue, Mar 24, 2015 at 8:25 AM, <arpita@i2sbs.com> wrote: Hi all, I am adding and correcting some points inline. On an unrelated note, maybe to save time and not create confusion, we should have technical discussions when I am around so that Marilza gets answers to her queries quickly. Warm Regards, Arpita Roy Practice Lead (WebSphere Technologies) i2s Business Solutions India Pvt Ltd No:3421, 10th Main 3rd cross, 100 Feet Road, Indira Nagar II stage, Bangalore –560038. Mobile: +91-9008555443 (India), +94-765248219 (Sri Lanka) www.i2sbs.com From: Prasad Kularatne [mailto:prasad@n-able.biz] Sent: Tuesday, March 24, 2015 5:32 AM To: Arpita Roy; Amila Hendahewa; Suneth Kariyawasam; Shirley Nanayakkara Cc: Marilza Maia; Can P Boyacigiller; Ajith Kumar; Scott Glen; Dishagi Ratnapriya; Krishnaraju Subject: IBM Consulting for SLT SOA/BPM project - Day1 Team, Thanks for joining the productive first-day session with Marilza. I've captured the following points that were discussed during the session; 1. [arpita@i2sbs.com] First and foremost, it was decided that Marilza will show us how to develop one flow (on which we have not worked at all) using the Telco Pack. Since we are already in progress with most of the remaining flows, we shall not be touching those. Also, since we are all new to the Telco Pack approach, we shall have to carefully consider if we shall be following this approach after this workshop [given the fact that our process models are significantly different from the process model in the Telco Pack for order handling, the developers’ inexperience with Telco Pack (for some even BPM) and the late stage of development for most of the flows, there are equal chances of slowing down as accelerating compared to the current approach]. We also need to see the causes of our current pace – if it is because data/information unavailability (not yet shared by SLT as in the case of ) or skillsets issues, those won’t change irrespective of the approach taken; in which case it won’t help our cause. However, for learning purposes and to verify whether we can go ahead with this method, we are going to first try out one flow while Marilza is here and she’d also show us the proper data and interface usage from the Telco Pack which we could use going forward. 2.Some specific process flows in the BWL were reviewed. Following key points were highlighted; a) [arpita@i2sbs.com] Some parts of the To-Be process model (as highlighted in a different color and explained to SLT) will not be implemented ‘in the current phase of implementation’. However, going forward SLT may want to implement those. Marilza feels that some of the tasks on the process models (like Approval of order, etc.) should be done by CRM as activities prior to sending the order to the order handling flow and should not be part of the order handling flow. It was explained that these tasks appear on the model because the customer feels that in their case these will not be handled by CRM but rather inside the order handling flow. Since this is the way the customer wants business to go on, we are going to implement those. It was noted that the To-Be process models which were used as the basis of design and development had those tasks that will not be implemented. There were CRM specific tasks as well as those tasks that will be implemented in future. Arpita highlighted the fact that SLT was adamant that those CRM specific tasks should appear in the To-Be Process models. b) For design and development, BWL process model should only have that part of the order handling flow which we are implementing. Therefore it was decided to derive only the OH flows from the to-be models and create a separate set of BP flows that will be used for design and development. Marilza re-iterated that fact that in a model-driven development, it is important to have process models of which all the tasks will be implemented. It was agreed that these models will be part of the Macro-design document. c) Marilza recommended to complete the input and output values for each process flow in the BWL to facilitate the developers to carry out development tasks. d) [arpita@i2sbs.com] Marilza raised some concerns about the To-Be Process Models differing from the Telco Pack Process Models. 3. We briefly discussed the SID mapping approach we took and the number of SID extensions the mapping process resulted in. Marilza indicated that she see a lack of understanding of SID by the team. Arpita acknowledged that she was doing this type of exercise for the first time. For an extensive data mapping exercise it was identified that a deeper knowledge of SID model and its structure is very important. Marilza will help us with SID mapping later in this engagement. It was also identified that more the number of extensions we have less will be the value of SID mapping. 4. [arpita@i2sbs.com] Marilza only checked with us if the exceptions/errors will be logged in a table. We explained her the audit/logging method and she was okay with it. Marilza recommended to have a separate database for handling technical exceptions/errors. We will have to also review the Exception handling flow with her later in the engagement. 5. [arpita@i2sbs.com] Marilza indicated that the SID-to-SLT-specific data mappings and the actual backend calls OSS/BSS should be built separately as access services. This effectively means that the IIB services built so far have to be divided into two parts – a mapping service and an actual backend call service. Marilza indicated that the services we've developed thus far in the ESB are "Access Services" or "Adapters" for Billing and Provisioning system operations. She also mentioned the importance of understanding the re-usability of these Access Services by different Business Services that would be exposed to BPM. She indicated that building of Business Services as composite services that combines a set of Access Services should be a design time task. Further discussion on these design points will be carried out when we go through the best practice design approach using "Extended Modification" process flow. 6. [arpita@i2sbs.com] The data usage is as per Scott’s advice (as attached with this mail). Later in the evening, Shirley showed the BPM Telecom Pack assets that were used from the PD. It was understood that we have not installed BPM Telecom Pack in the Process Center development server, however are using some of the assets in the PD only. We have the BPM Telecom Pack v7.5.0.0 and Marilza indicated that it is important to download and iFix without which this version of BPM Telecom Pack will not work with PD 8.5.5. Shirley was requested to open a PMR and get the iFix downloaded. Marilza indicated that she wants to know from where we got the XML schema files for data mapping as the Customer Order message available in BPM Telecom Pack was different in structure to what we've generated as part of our mapping. 7. Marilza indicated the importance of doing house-keeping tasks on the Process Center in order to clean-up the old snapshots. She indicated that she will point us to scripts that would help us to do this. Without such house-keeping, it is normal for us to observe degraded performance over time with PD and PC. By copy Arpita, If there are any specific recommendations given by Marilza during the review of the flows during my absence, please add those, tks.
19 | Day 5 Walk through the TC session | 2015-03-29 | MOM reply on Prasad Intrepretation | Re: IBM Consulting for SLT SOA/BPM project - Day5 | Hi Arpita, Now that you are clearly aware of the recommendations for the implementation, I suggest you discuss with Project Architect and Scott as needed along with Marilza and take it forward in the future implementation tasks. Few things that Marilza strongly suggested need to be looked into if we are to be successful and timely in this project, 1. Data mapping must be redone (we've used old Telecom Pack assets resulting in a mapping exercise with large number of SID extensions, Marilza explained that our mapping is incomplete and potentially incorrect) 2. Process models are sufficiently detailed enough for developers to carry out development 3. Process models should be sufficiently different for MAC-D scenarios all the way from the parent flows 4. Process flow decisions needs to be externalized 5. Use-cases needs to be documented From my layman understanding these are very strong suggestions. If we do not strongly consider these now and adjust our implementation methodology accordingly, we may encounter significant delays later. On Sun, Mar 29, 2015 at 2:14 PM, <arpita@i2sbs.com> wrote: Hi, Please find some updates inline. Warm Regards, Arpita Roy Practice Lead (WebSphere Technologies) i2s Business Solutions India Pvt Ltd No:3421, 10th Main 3rd cross, 100 Feet Road, Indira Nagar II stage, Bangalore –560038. Mobile: +91-9008555443 (India), +94-765248219 (Sri Lanka) www.i2sbs.com From: Prasad Kularatne [mailto:prasad@n-able.biz] Sent: Sunday, March 29, 2015 1:41 PM To: Arpita Roy Cc: Amila Hendahewa; Suneth Kariyawasam; Shirley Nanayakkara; Marilza Maia; Can P Boyacigiller; Ajith Kumar; Scott Glen; Dishagi Ratnapriya; Krishnaraju Subject: Re: IBM Consulting for SLT SOA/BPM project - Day5 Hi all, With Marilza's concerns on the process flows we developed and the level of detail present in the models given to the developers, we wanted her to address these concerns by walking us through the flow as this has a significant bearing on the future activities of the project and the speed at which we complete the development tasks. 1, Process flow review: As per the request made in the day-4 session, Marilza went a little deeper into the process flows we've modeled. Marilza highlighted her concerns. a) [arpita@i2sbs.com] The first thing which Marilza pointed out and which the technical team also feels is that having different architects (initially Scott, then Andrew, then Marilza) frequently to review and recommend changes when each architect has his or her unique outlook may create conflicts and confusion for the team and add a lot of rework. Also any changes suggested cannot be implemented directly without consulting the project architect. b) Major concern was that MAC-D (Move, Add, Change and Delete) processes were exactly the same at the parent process flow level. Even at sub-flow level they appeared to be same and even the API called identified for each sub-flow was exactly the same across Create and Delete flows (we've documented all API calls for all MAC-D scenarios). Difference in logic could be identified deeper down in the flow only. c) Marilza highlighted the importance of the need to make these process flows different from the top most level. She strongly indicated this need as our process flows have to be self-descriptive. She showed a presentation from Can-Paul which indicated the level of re-usability that is typically present in MAC-D processes. She showed that each such process is different even from the top level. Arpita first felt that what she has done is in line with Scott's recommendations, however, she agreed the need to have the MAC-D process differences identified all the way from the top level. She agreed to work on this. [arpita@i2sbs.com] I understood Marilza’s recommendations. However, I did not immediately commit on making the changes. What I agreed upon is renaming some of the sub-processes for clearer understanding of an external reviewer who wasn’t previously involved in the project. For most other points (as highlighted in the previous mail) that since these are recommendations for implementation, we need to have a discussion with the technical team and especially the project architect and only after that decide which way to proceed depending on the real acceleration the new approach can provide. Also we may have to check with Scott on a couple of things in this regard. d) Marilza indicated the need to externalize decisions into ODM. There was a discussion on when and how to externalize the decisions and the importance of doing it to improve business agility. In our process flows we have not identified those decisions which should be externalized. Marilza indicated that it should be done by the BA (Arpita) with the direction of the Solution Architect (Ajith). e) Marilza also highlighted the need to have more details in our process flows that will be given to developers to avoid the room for developers to think on their own those that should be finalized at the BA level. She indicated that those flows have to be drilled down all the way to eTOM level-5 as much as possible. We need little more guidance as to how Arpita can effect this in the flows already done. [arpita@i2sbs.com] There is not a proper eTOM level 5. What Marilza meant was to drill the process models down to the API level everywhere. f) She also highlighted the importance of documenting use-cases in a self-descriptive format. She indicated the importance of doing this as the test-cases would be derived on this. SOA team felt the importance of getting an agreement on the use-cases for each MAC-D we are to implement without which it would be difficult to agree on the test-cases. Marilza showed a properly documented use-cases for MAC-D processes. [arpita@i2sbs.com] Again, since these are recommendations for implementation, we need to have a discussion with the technical team and especially the project architect and only after that decide which way to proceed. Also we may have to check with Scott on a couple of things in this regard. g) Marilza indicated the need to have a Master test plan including testing of services, unit testing of sub-flows, integration testing etc. [arpita@i2sbs.com] This wasn’t discussed with me. However, I would imagine that the SOA team who discussed this point must have informed Marilza that the test strategy and test plan are already under progress by the test team. 2. Meeting with Oracle Consulting Services: At our request, SLT arranged this meeting to help us understand how Oracle Consulting Services (OCS) plan to implement Siebel CRM in respect or Order handling and their expectation from the SOA layer. As part of our scope, we are expected to externalize any enrichment required to the SO so that it is in an acceptable format to the SLT Provisioning system. Our plan had b een to use an external mock-up service for this enrichment as there is no catalog existing at the moment. Marilza's indicated that we should build a process flow in a manner that there will be no change once the catalog for order decomposition is introduced. This is what we have communicated to SLT as well. The discussion focused largely on the use of catalog and how decomposition in different layers will be achieved. Following points were discussed; a) As per the finalized scope, OCS will not be implementing PH4C (Oracle Product Hub for Communications) in the initial phase. Siebel CRM will be Customer Master and will use its internal catalog for Commercial Product decomposition. Their internal catalog will not store any technical details of the order. This means that another external catalog is required to maintain the details of technical decomposition giving rise to the need for two catalogs referencing product data and two sets of details associated with such data. [arpita@i2sbs.com] SLT team insisted that PH4C Product Catalog must be implemented during the first phase and Oracle team said that they will internally discuss with their architect and other experts and come back on this. b) Marilza strongly argued the need to have one catalog to store details of Commercial to CFS, CFS to RFS and even logical to physical resources (however today logical to physical resource mapping is handled inside their provisioning system). She explained why this is needed and SLT thinking was inline with her explanation. Basically she strongly highlighted the unnecessary burden of catalog synchronization for order decomposition if two catalogs are to be maintained. c) OCS did not have an answer as to how they should handle the order process with a single catalog which will be queried by Siebel for commercial to CFS order decomposition by the CRM and CFS to RFS by the Order handling code. SLT highlighted absence of this information means that Siebel will not be able to complete the order processing with their vision of a single catalog. Therefore the discussion got concluded with OCS informing us that they will come up with their strategy to address a single catalog vision of SLT. 3. BPM performance analysis and housekeeping tasks: Marilza demonstrated the key housekeeping tasks that we should carry out on an ongoing basis, either through scheduling or manually by an administrator. She also indicated the pre-built scripts that comes with BPM that should be used. She indicated that the performance of the process center can be sizeably improved by routinely carrying out these tasks. She also highlighted the architecture of the 3-cluster Golden topology recommended by Scott which we must implement for the production environment during IBM BPM implementation. We also requested Marilza to share with the SOA team the content pertaining to important concepts she explained throughout the session, tks. On Sat, Mar 28, 2015 at 7:04 AM, Prasad Kularatne <prasad@n-able.biz> wrote: Hi all, Today's session was intended at walking the team through the SID data mapping exercise. We understood the importance of doing this exercise with the BSS vendor as the data mapping requires a deeper understanding of the the fields/elements for each back-end operation we will be using within our scope. I thought it was a very effective day for the team as they could really see the real acceleration provided by Telecom Pack. By copy Arpita, please update, add any points I might have missed. 1. Telecom Pack version: Importance of correct up-to-date Telecom Pack version was highlighted. Since we had used an older version of telecom pack, the data mapping we've already done in incomplete and the exercise should be carried out again. Marilza recommended us to use Telecom Pack v7.5.0.0 with iFix JR51530 Note: At this point, I feel that we should involve BSS vendor in this exercise and since we have to carry out the data mapping activity again, my suggestion is that we go ahead with the latest BSS system API's, this will allow us to get more support from the vendor which we is lacking at the moment. 2. SID data mapping exercise: Marilza demonstrated how SID data mapping exercise should be carried out with the use of Telecom Pack assets. It was basically a top-down approach. Once our implementable flows are finalized, we can map API calls invoked at each task to the TAM operations defined in Telecom Pack. Marilza also explained how the data mapping can be carried out and the need to update the extensions in the SID objects inside PD. Once this exercise is carried out, we can import the TAM operation into IIB which in tern will create the appropriate Integration Service. Once the Integration service is created in IIB, we can build the message flows to do the native-to-SID transformations. Suneth felt this methodology can potentially accelerate the data mapping exercise at least 2-3 times compared to the approach he took initially. 3. Process flow design review: Marilza indicated that importance of having separate process flows from ground up for Move, Add, Change, Delete (MAC-D) scenarios as each such business process is different. She also mentioned that when we model such process flows they should be sufficiently generic to handle orders for different types of products. Arpita agreed to get her expert advice on improving the flows. 5. Involvement of the Solution Architect: Marilza indicated that it would be important for Solution Architect to involve more in the design and development to drive the architectural decisions. More involved decisions relating to externalizing of decisions within process flow into ODM and determination of composite vs. atomic services were some of the areas Marilza thinks the Solution Architects involvement is required. 6. Level of detail required in Process Flows: Marilza's review indicated that the process models when passed on to the developers from the BA would required to be at a more detailed level. She suggested to always look into breaking the processes all the way down to eTOM level-5 as much as possible. More details on the input/output messages points at which we externalized decisions into ODM and detailed contextual documentation were recommended to be included in the process models once they are broken down into much more details level where possible. 7. Developers role: Marilza highlighted the importance of developers role in BPM development. They should question the BA and architect to drill down and understand the process flow better before starting their development. Thanks. On Wed, Mar 25, 2015 at 7:34 AM, <arpita@i2sbs.com> wrote: Hi all, Please find the updates on some of the points inline. Warm Regards, Arpita Roy Practice Lead (WebSphere Technologies) i2s Business Solutions India Pvt Ltd No:3421, 10th Main 3rd cross, 100 Feet Road, Indira Nagar II stage, Bangalore –560038. Mobile: +91-9008555443 (India), +94-765248219 (Sri Lanka) www.i2sbs.com From: Prasad Kularatne [mailto:prasad@n-able.biz] Sent: Wednesday, March 25, 2015 3:32 AM To: Arpita Roy Cc: Amila Hendahewa; Suneth Kariyawasam; Shirley Nanayakkara; Marilza Maia; Can P Boyacigiller; Ajith Kumar; Scott Glen; Dishagi Ratnapriya; Krishnaraju Subject: Re: IBM Consulting for SLT SOA/BPM project - Day2 Hi all, Today's session started off with the installation of Telecom Pack assets on an SOA team members laptop to be used in the remaining part of the consulting engagement. By copy Arpita, please update, add any points I might have missed. 1. Marilza demonstrated how to resolve the dependency conflicts that arose when we started installing all the toolkits that comes with Telecom Pack 7.5.0.0 iFix JR48588. Finally we managed to have this version of telecom pack assets loaded into Shirley's laptop into a Process Center environment at N-able. 2. [arpita@i2sbs.com] We used one of smaller sub-processes “Track Service Provisioning Activity” inside the “Track & Manage Orders” sub-process from the “Extended Modifications” flow. This sub-process has one callback (which Marilza considers as a notification), 2 notification tasks and only one activity (Manage Customer Billing) which has 4 API calls to backend billing system. We used "Extended Modification" flow to understand the use of Telecom pack and how it will help us to accelerate our development. We used "Manage Customer Billing" activity within the process flow and started modeling it using Telecom Pack assets. 3. [arpita@i2sbs.com] We did not map our operations to TAM Applications and Operations, rather we only found from the Telco Pack Service Model (an excel sheet which comes with the ifix) the appropriate Telco Pack operation corresponding to our operation so that we can find the input and output of these operations. Currently, in the TP service model related resource interfaces (which contain these operations) are clubbed together and mapped to a particular TAM application. Using "Manage Customer Billing" as an example, Marilza demonstrated how to use BPM Telecom Pack. She demonstrated the need to understand the TAM Service Interfaces that contain "TAM Operations" we execute against the target systems within the activity. Within the above activity, we modeled a sub-flow and we found four operations to be executed against the BSS system and started mapping those to TAM Operations. She demonstrated how to import such operations in PD from the appropriate Telecom Pack toolkit and how we get the input and output message structures automatically in PD. 4. [arpita@i2sbs.com] Suneth/Shirley highlighted how when this exercise was being done originally they could not complete the allocated tasks (to get the descriptions of all the elements in the requests and responses of the API operations) because when they spoke to the SLT team they were unaware of the descriptions of the elements. Prasad suggested that we take up this work again with the BSS vendor to see if they know the appropriate descriptions. Once the Operations were mapped, we started the exercise of data mapping. As a preparation for that all relevant operations and elements of those operations were imported into an Excel sheet. During this exercise, we found certain elements in the SLT BSS operations were very specific to SLT BSS system and there was inadequate documentation (only Java doc) available to understand the use of these elements. Suneth/Shirley felt the need to work with BSS vendor team during the data mapping exercise to have a better understanding of these elements and therefore carry out the correct mapping into the SID data model. 5. There was a concern by the SOA team that during the data mapping, there were lots of elements that we could not map to a corresponding SID element and we therefore treated them as extensions. Marilza found out that we were using specific toolkits from a version of Telecom pack older than the one comes with iFix JR48588, and the organization of the Business Objects in that version was different to the one that comes with iFix JR48588. Taking "Customer Order" business object, she showed how different the organization of elements in the older version we were using and the one that comes with JR48588. This may be one of the reasons SOA team data mapping exercise resulted in a significant number of SID extensions. With the JR48588 toolkits, due to the hierarchical organization of related business objects, the mapping exercise would have been much easier and the team could have found the relevant entities easier. 6. Marilza indicated that she will get the latest recommended iFix version for the use in this project. On the third day we expect Marilza to help us in SID data mapping exercise and now that we have Operations from SLT BSS system with their elements and the relevant SID entities in Excel format, we can start the mapping activity from the morning with i2S team also connected via WebEx. We also plan to meet SLT, the Siebel project team, to understand how the order handling will happen with the new CRM implementation. The objective of this discussion is to understand how we should carry out order decomposition and issuing the RFS order to SLT OSS system. Currently what we've agreed with SLT was that we will use an external Stub Service to do the mapping (we will hard-code the required CFS to RFS mapping) however, we have not started analysis of their service order messages going to OSS or BSS yet. [arpita@i2sbs.com] Again, we are not going to do any mapping from CFS to RFS in the stub service. The stub service will have the hard-coded decomposition for each products(not CFS). Practically, because this will be a hard-coded response, it will be exactly for a given products, irrespective of what CFS are being passed. On Tue, Mar 24, 2015 at 8:25 AM, <arpita@i2sbs.com> wrote: Hi all, I am adding and correcting some points inline. On an unrelated note, maybe to save time and not create confusion, we should have technical discussions when I am around so that Marilza gets answers to her queries quickly. Warm Regards, Arpita Roy Practice Lead (WebSphere Technologies) i2s Business Solutions India Pvt Ltd No:3421, 10th Main 3rd cross, 100 Feet Road, Indira Nagar II stage, Bangalore –560038. Mobile: +91-9008555443 (India), +94-765248219 (Sri Lanka) www.i2sbs.com From: Prasad Kularatne [mailto:prasad@n-able.biz] Sent: Tuesday, March 24, 2015 5:32 AM To: Arpita Roy; Amila Hendahewa; Suneth Kariyawasam; Shirley Nanayakkara Cc: Marilza Maia; Can P Boyacigiller; Ajith Kumar; Scott Glen; Dishagi Ratnapriya; Krishnaraju Subject: IBM Consulting for SLT SOA/BPM project - Day1 Team, Thanks for joining the productive first-day session with Marilza. I've captured the following points that were discussed during the session; 1. [arpita@i2sbs.com] First and foremost, it was decided that Marilza will show us how to develop one flow (on which we have not worked at all) using the Telco Pack. Since we are already in progress with most of the remaining flows, we shall not be touching those. Also, since we are all new to the Telco Pack approach, we shall have to carefully consider if we shall be following this approach after this workshop [given the fact that our process models are significantly different from the process model in the Telco Pack for order handling, the developers’ inexperience with Telco Pack (for some even BPM) and the late stage of development for most of the flows, there are equal chances of slowing down as accelerating compared to the current approach]. We also need to see the causes of our current pace – if it is because data/information unavailability (not yet shared by SLT as in the case of ) or skillsets issues, those won’t change irrespective of the approach taken; in which case it won’t help our cause. However, for learning purposes and to verify whether we can go ahead with this method, we are going to first try out one flow while Marilza is here and she’d also show us the proper data and interface usage from the Telco Pack which we could use going forward. 2.Some specific process flows in the BWL were reviewed. Following key points were highlighted; a) [arpita@i2sbs.com] Some parts of the To-Be process model (as highlighted in a different color and explained to SLT) will not be implemented ‘in the current phase of implementation’. However, going forward SLT may want to implement those. Marilza feels that some of the tasks on the process models (like Approval of order, etc.) should be done by CRM as activities prior to sending the order to the order handling flow and should not be part of the order handling flow. It was explained that these tasks appear on the model because the customer feels that in their case these will not be handled by CRM but rather inside the order handling flow. Since this is the way the customer wants business to go on, we are going to implement those. It was noted that the To-Be process models which were used as the basis of design and development had those tasks that will not be implemented. There were CRM specific tasks as well as those tasks that will be implemented in future. Arpita highlighted the fact that SLT was adamant that those CRM specific tasks should appear in the To-Be Process models. b) For design and development, BWL process model should only have that part of the order handling flow which we are implementing. Therefore it was decided to derive only the OH flows from the to-be models and create a separate set of BP flows that will be used for design and development. Marilza re-iterated that fact that in a model-driven development, it is important to have process models of which all the tasks will be implemented. It was agreed that these models will be part of the Macro-design document. c) Marilza recommended to complete the input and output values for each process flow in the BWL to facilitate the developers to carry out development tasks. d) [arpita@i2sbs.com] Marilza raised some concerns about the To-Be Process Models differing from the Telco Pack Process Models. 3. We briefly discussed the SID mapping approach we took and the number of SID extensions the mapping process resulted in. Marilza indicated that she see a lack of understanding of SID by the team. Arpita acknowledged that she was doing this type of exercise for the first time. For an extensive data mapping exercise it was identified that a deeper knowledge of SID model and its structure is very important. Marilza will help us with SID mapping later in this engagement. It was also identified that more the number of extensions we have less will be the value of SID mapping. 4. [arpita@i2sbs.com] Marilza only checked with us if the exceptions/errors will be logged in a table. We explained her the audit/logging method and she was okay with it. Marilza recommended to have a separate database for handling technical exceptions/errors. We will have to also review the Exception handling flow with her later in the engagement. 5. [arpita@i2sbs.com] Marilza indicated that the SID-to-SLT-specific data mappings and the actual backend calls OSS/BSS should be built separately as access services. This effectively means that the IIB services built so far have to be divided into two parts – a mapping service and an actual backend call service. Marilza indicated that the services we've developed thus far in the ESB are "Access Services" or "Adapters" for Billing and Provisioning system operations. She also mentioned the importance of understanding the re-usability of these Access Services by different Business Services that would be exposed to BPM. She indicated that building of Business Services as composite services that combines a set of Access Services should be a design time task. Further discussion on these design points will be carried out when we go through the best practice design approach using "Extended Modification" process flow. 6. [arpita@i2sbs.com] The data usage is as per Scott’s advice (as attached with this mail). Later in the evening, Shirley showed the BPM Telecom Pack assets that were used from the PD. It was understood that we have not installed BPM Telecom Pack in the Process Center development server, however are using some of the assets in the PD only. We have the BPM Telecom Pack v7.5.0.0 and Marilza indicated that it is important to download and iFix without which this version of BPM Telecom Pack will not work with PD 8.5.5. Shirley was requested to open a PMR and get the iFix downloaded. Marilza indicated that she wants to know from where we got the XML schema files for data mapping as the Customer Order message available in BPM Telecom Pack was different in structure to what we've generated as part of our mapping. 7. Marilza indicated the importance of doing house-keeping tasks on the Process Center in order to clean-up the old snapshots. She indicated that she will point us to scripts that would help us to do this. Without such house-keeping, it is normal for us to observe degraded performance over time with PD and PC. By copy Arpita, If there are any specific recommendations given by Marilza during the review of the flows during my absence, please add those, tks.
20 | Prasad reply on Arpita comments | 2015-03-29 | Prasad reply on Arpita comments | Re: IBM Consulting for SLT SOA/BPM project - Day5 | Hi Arpita, On the use of Architects Scott, Andrew and Marilza, kindly note they were involved for specific reasons as the SOA team needed help to continue with the project scope. If they were not involved project would not have moved to this level. We haven't had no experience in eTOM process alignment, SID data mapping etc. What we should do is to welcome their recommendations and if there are conflicts, which honestly I didn't see any from what I know, review it openly discuss with project architect and move on. Scott: SOA project team did not have prior experience in eTOM alignment of as-is business process models, hence expertise is required from IBM. Scott also helped and reviewed customer concerns on the ADD (create) process model and highlighted the need to remove CRM related tasks from the Order Handling flow. He did not review the whole MAC-D flows, hence he would not have recommended on the need to have each MAC-D flow different all the way from the parent flow. Andrew: SLT was not ready to accept the to-be ADD (create) process model as the aligned eTOM processes did not reflect the way business is carried out and therefore we felt the need to involve Scott again. Due to his unavailability Andrew stepped in. Marilza: SOA project team wanted mentoring on the use of Telecom Pack assets to accelerate the development. SOA project team, as you highlighted did not have prior experience in SID data mapping, hence we wanted her to take us through the process. I did not see anything conflicting that resulted in re-work up to now neither has Shirley nor Suneth. It is OK to discuss with Project Architect and adopt their recommendations appropriately, however those are, as I see, basic principles of an SOA design. 1. Level of detail required in process models - self-describing process models. 2. Externalizing decision points in the process as much as possible 3. Completely different flows for MAC-D 4. SID data mapping from operations down to elements and accelerate the exercise using telecom pack One of the key criteria of engaging i2S for the SLT SOA/BPM project was the promise that the team will use IBM Best Practices in the deployment as the team consisted of many former IBMers. Therefore I kindly expect you to take these recommendations in a positive note and adopt them as much as possible to avoid delays later, tks. On Sun, Mar 29, 2015 at 2:14 PM, <arpita@i2sbs.com> wrote: Hi, Please find some updates inline. Warm Regards, Arpita Roy Practice Lead (WebSphere Technologies) i2s Business Solutions India Pvt Ltd No:3421, 10th Main 3rd cross, 100 Feet Road, Indira Nagar II stage, Bangalore –560038. Mobile: +91-9008555443 (India), +94-765248219 (Sri Lanka) www.i2sbs.com From: Prasad Kularatne [mailto:prasad@n-able.biz] Sent: Sunday, March 29, 2015 1:41 PM To: Arpita Roy Cc: Amila Hendahewa; Suneth Kariyawasam; Shirley Nanayakkara; Marilza Maia; Can P Boyacigiller; Ajith Kumar; Scott Glen; Dishagi Ratnapriya; Krishnaraju Subject: Re: IBM Consulting for SLT SOA/BPM project - Day5 Hi all, With Marilza's concerns on the process flows we developed and the level of detail present in the models given to the developers, we wanted her to address these concerns by walking us through the flow as this has a significant bearing on the future activities of the project and the speed at which we complete the development tasks. 1, Process flow review: As per the request made in the day-4 session, Marilza went a little deeper into the process flows we've modeled. Marilza highlighted her concerns. a) [arpita@i2sbs.com] The first thing which Marilza pointed out and which the technical team also feels is that having different architects (initially Scott, then Andrew, then Marilza) frequently to review and recommend changes when each architect has his or her unique outlook may create conflicts and confusion for the team and add a lot of rework. Also any changes suggested cannot be implemented directly without consulting the project architect. b) Major concern was that MAC-D (Move, Add, Change and Delete) processes were exactly the same at the parent process flow level. Even at sub-flow level they appeared to be same and even the API called identified for each sub-flow was exactly the same across Create and Delete flows (we've documented all API calls for all MAC-D scenarios). Difference in logic could be identified deeper down in the flow only. c) Marilza highlighted the importance of the need to make these process flows different from the top most level. She strongly indicated this need as our process flows have to be self-descriptive. She showed a presentation from Can-Paul which indicated the level of re-usability that is typically present in MAC-D processes. She showed that each such process is different even from the top level. Arpita first felt that what she has done is in line with Scott's recommendations, however, she agreed the need to have the MAC-D process differences identified all the way from the top level. She agreed to work on this. [arpita@i2sbs.com] I understood Marilza’s recommendations. However, I did not immediately commit on making the changes. What I agreed upon is renaming some of the sub-processes for clearer understanding of an external reviewer who wasn’t previously involved in the project. For most other points (as highlighted in the previous mail) that since these are recommendations for implementation, we need to have a discussion with the technical team and especially the project architect and only after that decide which way to proceed depending on the real acceleration the new approach can provide. Also we may have to check with Scott on a couple of things in this regard. d) Marilza indicated the need to externalize decisions into ODM. There was a discussion on when and how to externalize the decisions and the importance of doing it to improve business agility. In our process flows we have not identified those decisions which should be externalized. Marilza indicated that it should be done by the BA (Arpita) with the direction of the Solution Architect (Ajith). e) Marilza also highlighted the need to have more details in our process flows that will be given to developers to avoid the room for developers to think on their own those that should be finalized at the BA level. She indicated that those flows have to be drilled down all the way to eTOM level-5 as much as possible. We need little more guidance as to how Arpita can effect this in the flows already done. [arpita@i2sbs.com] There is not a proper eTOM level 5. What Marilza meant was to drill the process models down to the API level everywhere. f) She also highlighted the importance of documenting use-cases in a self-descriptive format. She indicated the importance of doing this as the test-cases would be derived on this. SOA team felt the importance of getting an agreement on the use-cases for each MAC-D we are to implement without which it would be difficult to agree on the test-cases. Marilza showed a properly documented use-cases for MAC-D processes. [arpita@i2sbs.com] Again, since these are recommendations for implementation, we need to have a discussion with the technical team and especially the project architect and only after that decide which way to proceed. Also we may have to check with Scott on a couple of things in this regard. g) Marilza indicated the need to have a Master test plan including testing of services, unit testing of sub-flows, integration testing etc. [arpita@i2sbs.com] This wasn’t discussed with me. However, I would imagine that the SOA team who discussed this point must have informed Marilza that the test strategy and test plan are already under progress by the test team. 2. Meeting with Oracle Consulting Services: At our request, SLT arranged this meeting to help us understand how Oracle Consulting Services (OCS) plan to implement Siebel CRM in respect or Order handling and their expectation from the SOA layer. As part of our scope, we are expected to externalize any enrichment required to the SO so that it is in an acceptable format to the SLT Provisioning system. Our plan had b een to use an external mock-up service for this enrichment as there is no catalog existing at the moment. Marilza's indicated that we should build a process flow in a manner that there will be no change once the catalog for order decomposition is introduced. This is what we have communicated to SLT as well. The discussion focused largely on the use of catalog and how decomposition in different layers will be achieved. Following points were discussed; a) As per the finalized scope, OCS will not be implementing PH4C (Oracle Product Hub for Communications) in the initial phase. Siebel CRM will be Customer Master and will use its internal catalog for Commercial Product decomposition. Their internal catalog will not store any technical details of the order. This means that another external catalog is required to maintain the details of technical decomposition giving rise to the need for two catalogs referencing product data and two sets of details associated with such data. [arpita@i2sbs.com] SLT team insisted that PH4C Product Catalog must be implemented during the first phase and Oracle team said that they will internally discuss with their architect and other experts and come back on this. b) Marilza strongly argued the need to have one catalog to store details of Commercial to CFS, CFS to RFS and even logical to physical resources (however today logical to physical resource mapping is handled inside their provisioning system). She explained why this is needed and SLT thinking was inline with her explanation. Basically she strongly highlighted the unnecessary burden of catalog synchronization for order decomposition if two catalogs are to be maintained. c) OCS did not have an answer as to how they should handle the order process with a single catalog which will be queried by Siebel for commercial to CFS order decomposition by the CRM and CFS to RFS by the Order handling code. SLT highlighted absence of this information means that Siebel will not be able to complete the order processing with their vision of a single catalog. Therefore the discussion got concluded with OCS informing us that they will come up with their strategy to address a single catalog vision of SLT. 3. BPM performance analysis and housekeeping tasks: Marilza demonstrated the key housekeeping tasks that we should carry out on an ongoing basis, either through scheduling or manually by an administrator. She also indicated the pre-built scripts that comes with BPM that should be used. She indicated that the performance of the process center can be sizeably improved by routinely carrying out these tasks. She also highlighted the architecture of the 3-cluster Golden topology recommended by Scott which we must implement for the production environment during IBM BPM implementation. We also requested Marilza to share with the SOA team the content pertaining to important concepts she explained throughout the session, tks. On Sat, Mar 28, 2015 at 7:04 AM, Prasad Kularatne <prasad@n-able.biz> wrote: Hi all, Today's session was intended at walking the team through the SID data mapping exercise. We understood the importance of doing this exercise with the BSS vendor as the data mapping requires a deeper understanding of the the fields/elements for each back-end operation we will be using within our scope. I thought it was a very effective day for the team as they could really see the real acceleration provided by Telecom Pack. By copy Arpita, please update, add any points I might have missed. 1. Telecom Pack version: Importance of correct up-to-date Telecom Pack version was highlighted. Since we had used an older version of telecom pack, the data mapping we've already done in incomplete and the exercise should be carried out again. Marilza recommended us to use Telecom Pack v7.5.0.0 with iFix JR51530 Note: At this point, I feel that we should involve BSS vendor in this exercise and since we have to carry out the data mapping activity again, my suggestion is that we go ahead with the latest BSS system API's, this will allow us to get more support from the vendor which we is lacking at the moment. 2. SID data mapping exercise: Marilza demonstrated how SID data mapping exercise should be carried out with the use of Telecom Pack assets. It was basically a top-down approach. Once our implementable flows are finalized, we can map API calls invoked at each task to the TAM operations defined in Telecom Pack. Marilza also explained how the data mapping can be carried out and the need to update the extensions in the SID objects inside PD. Once this exercise is carried out, we can import the TAM operation into IIB which in tern will create the appropriate Integration Service. Once the Integration service is created in IIB, we can build the message flows to do the native-to-SID transformations. Suneth felt this methodology can potentially accelerate the data mapping exercise at least 2-3 times compared to the approach he took initially. 3. Process flow design review: Marilza indicated that importance of having separate process flows from ground up for Move, Add, Change, Delete (MAC-D) scenarios as each such business process is different. She also mentioned that when we model such process flows they should be sufficiently generic to handle orders for different types of products. Arpita agreed to get her expert advice on improving the flows. 5. Involvement of the Solution Architect: Marilza indicated that it would be important for Solution Architect to involve more in the design and development to drive the architectural decisions. More involved decisions relating to externalizing of decisions within process flow into ODM and determination of composite vs. atomic services were some of the areas Marilza thinks the Solution Architects involvement is required. 6. Level of detail required in Process Flows: Marilza's review indicated that the process models when passed on to the developers from the BA would required to be at a more detailed level. She suggested to always look into breaking the processes all the way down to eTOM level-5 as much as possible. More details on the input/output messages points at which we externalized decisions into ODM and detailed contextual documentation were recommended to be included in the process models once they are broken down into much more details level where possible. 7. Developers role: Marilza highlighted the importance of developers role in BPM development. They should question the BA and architect to drill down and understand the process flow better before starting their development. Thanks. On Wed, Mar 25, 2015 at 7:34 AM, <arpita@i2sbs.com> wrote: Hi all, Please find the updates on some of the points inline. Warm Regards, Arpita Roy Practice Lead (WebSphere Technologies) i2s Business Solutions India Pvt Ltd No:3421, 10th Main 3rd cross, 100 Feet Road, Indira Nagar II stage, Bangalore –560038. Mobile: +91-9008555443 (India), +94-765248219 (Sri Lanka) www.i2sbs.com From: Prasad Kularatne [mailto:prasad@n-able.biz] Sent: Wednesday, March 25, 2015 3:32 AM To: Arpita Roy Cc: Amila Hendahewa; Suneth Kariyawasam; Shirley Nanayakkara; Marilza Maia; Can P Boyacigiller; Ajith Kumar; Scott Glen; Dishagi Ratnapriya; Krishnaraju Subject: Re: IBM Consulting for SLT SOA/BPM project - Day2 Hi all, Today's session started off with the installation of Telecom Pack assets on an SOA team members laptop to be used in the remaining part of the consulting engagement. By copy Arpita, please update, add any points I might have missed. 1. Marilza demonstrated how to resolve the dependency conflicts that arose when we started installing all the toolkits that comes with Telecom Pack 7.5.0.0 iFix JR48588. Finally we managed to have this version of telecom pack assets loaded into Shirley's laptop into a Process Center environment at N-able. 2. [arpita@i2sbs.com] We used one of smaller sub-processes “Track Service Provisioning Activity” inside the “Track & Manage Orders” sub-process from the “Extended Modifications” flow. This sub-process has one callback (which Marilza considers as a notification), 2 notification tasks and only one activity (Manage Customer Billing) which has 4 API calls to backend billing system. We used "Extended Modification" flow to understand the use of Telecom pack and how it will help us to accelerate our development. We used "Manage Customer Billing" activity within the process flow and started modeling it using Telecom Pack assets. 3. [arpita@i2sbs.com] We did not map our operations to TAM Applications and Operations, rather we only found from the Telco Pack Service Model (an excel sheet which comes with the ifix) the appropriate Telco Pack operation corresponding to our operation so that we can find the input and output of these operations. Currently, in the TP service model related resource interfaces (which contain these operations) are clubbed together and mapped to a particular TAM application. Using "Manage Customer Billing" as an example, Marilza demonstrated how to use BPM Telecom Pack. She demonstrated the need to understand the TAM Service Interfaces that contain "TAM Operations" we execute against the target systems within the activity. Within the above activity, we modeled a sub-flow and we found four operations to be executed against the BSS system and started mapping those to TAM Operations. She demonstrated how to import such operations in PD from the appropriate Telecom Pack toolkit and how we get the input and output message structures automatically in PD. 4. [arpita@i2sbs.com] Suneth/Shirley highlighted how when this exercise was being done originally they could not complete the allocated tasks (to get the descriptions of all the elements in the requests and responses of the API operations) because when they spoke to the SLT team they were unaware of the descriptions of the elements. Prasad suggested that we take up this work again with the BSS vendor to see if they know the appropriate descriptions. Once the Operations were mapped, we started the exercise of data mapping. As a preparation for that all relevant operations and elements of those operations were imported into an Excel sheet. During this exercise, we found certain elements in the SLT BSS operations were very specific to SLT BSS system and there was inadequate documentation (only Java doc) available to understand the use of these elements. Suneth/Shirley felt the need to work with BSS vendor team during the data mapping exercise to have a better understanding of these elements and therefore carry out the correct mapping into the SID data model. 5. There was a concern by the SOA team that during the data mapping, there were lots of elements that we could not map to a corresponding SID element and we therefore treated them as extensions. Marilza found out that we were using specific toolkits from a version of Telecom pack older than the one comes with iFix JR48588, and the organization of the Business Objects in that version was different to the one that comes with iFix JR48588. Taking "Customer Order" business object, she showed how different the organization of elements in the older version we were using and the one that comes with JR48588. This may be one of the reasons SOA team data mapping exercise resulted in a significant number of SID extensions. With the JR48588 toolkits, due to the hierarchical organization of related business objects, the mapping exercise would have been much easier and the team could have found the relevant entities easier. 6. Marilza indicated that she will get the latest recommended iFix version for the use in this project. On the third day we expect Marilza to help us in SID data mapping exercise and now that we have Operations from SLT BSS system with their elements and the relevant SID entities in Excel format, we can start the mapping activity from the morning with i2S team also connected via WebEx. We also plan to meet SLT, the Siebel project team, to understand how the order handling will happen with the new CRM implementation. The objective of this discussion is to understand how we should carry out order decomposition and issuing the RFS order to SLT OSS system. Currently what we've agreed with SLT was that we will use an external Stub Service to do the mapping (we will hard-code the required CFS to RFS mapping) however, we have not started analysis of their service order messages going to OSS or BSS yet. [arpita@i2sbs.com] Again, we are not going to do any mapping from CFS to RFS in the stub service. The stub service will have the hard-coded decomposition for each products(not CFS). Practically, because this will be a hard-coded response, it will be exactly for a given products, irrespective of what CFS are being passed. On Tue, Mar 24, 2015 at 8:25 AM, <arpita@i2sbs.com> wrote: Hi all, I am adding and correcting some points inline. On an unrelated note, maybe to save time and not create confusion, we should have technical discussions when I am around so that Marilza gets answers to her queries quickly. Warm Regards, Arpita Roy Practice Lead (WebSphere Technologies) i2s Business Solutions India Pvt Ltd No:3421, 10th Main 3rd cross, 100 Feet Road, Indira Nagar II stage, Bangalore –560038. Mobile: +91-9008555443 (India), +94-765248219 (Sri Lanka) www.i2sbs.com From: Prasad Kularatne [mailto:prasad@n-able.biz] Sent: Tuesday, March 24, 2015 5:32 AM To: Arpita Roy; Amila Hendahewa; Suneth Kariyawasam; Shirley Nanayakkara Cc: Marilza Maia; Can P Boyacigiller; Ajith Kumar; Scott Glen; Dishagi Ratnapriya; Krishnaraju Subject: IBM Consulting for SLT SOA/BPM project - Day1 Team, Thanks for joining the productive first-day session with Marilza. I've captured the following points that were discussed during the session; 1. [arpita@i2sbs.com] First and foremost, it was decided that Marilza will show us how to develop one flow (on which we have not worked at all) using the Telco Pack. Since we are already in progress with most of the remaining flows, we shall not be touching those. Also, since we are all new to the Telco Pack approach, we shall have to carefully consider if we shall be following this approach after this workshop [given the fact that our process models are significantly different from the process model in the Telco Pack for order handling, the developers’ inexperience with Telco Pack (for some even BPM) and the late stage of development for most of the flows, there are equal chances of slowing down as accelerating compared to the current approach]. We also need to see the causes of our current pace – if it is because data/information unavailability (not yet shared by SLT as in the case of ) or skillsets issues, those won’t change irrespective of the approach taken; in which case it won’t help our cause. However, for learning purposes and to verify whether we can go ahead with this method, we are going to first try out one flow while Marilza is here and she’d also show us the proper data and interface usage from the Telco Pack which we could use going forward. 2.Some specific process flows in the BWL were reviewed. Following key points were highlighted; a) [arpita@i2sbs.com] Some parts of the To-Be process model (as highlighted in a different color and explained to SLT) will not be implemented ‘in the current phase of implementation’. However, going forward SLT may want to implement those. Marilza feels that some of the tasks on the process models (like Approval of order, etc.) should be done by CRM as activities prior to sending the order to the order handling flow and should not be part of the order handling flow. It was explained that these tasks appear on the model because the customer feels that in their case these will not be handled by CRM but rather inside the order handling flow. Since this is the way the customer wants business to go on, we are going to implement those. It was noted that the To-Be process models which were used as the basis of design and development had those tasks that will not be implemented. There were CRM specific tasks as well as those tasks that will be implemented in future. Arpita highlighted the fact that SLT was adamant that those CRM specific tasks should appear in the To-Be Process models. b) For design and development, BWL process model should only have that part of the order handling flow which we are implementing. Therefore it was decided to derive only the OH flows from the to-be models and create a separate set of BP flows that will be used for design and development. Marilza re-iterated that fact that in a model-driven development, it is important to have process models of which all the tasks will be implemented. It was agreed that these models will be part of the Macro-design document. c) Marilza recommended to complete the input and output values for each process flow in the BWL to facilitate the developers to carry out development tasks. d) [arpita@i2sbs.com] Marilza raised some concerns about the To-Be Process Models differing from the Telco Pack Process Models. 3. We briefly discussed the SID mapping approach we took and the number of SID extensions the mapping process resulted in. Marilza indicated that she see a lack of understanding of SID by the team. Arpita acknowledged that she was doing this type of exercise for the first time. For an extensive data mapping exercise it was identified that a deeper knowledge of SID model and its structure is very important. Marilza will help us with SID mapping later in this engagement. It was also identified that more the number of extensions we have less will be the value of SID mapping. 4. [arpita@i2sbs.com] Marilza only checked with us if the exceptions/errors will be logged in a table. We explained her the audit/logging method and she was okay with it. Marilza recommended to have a separate database for handling technical exceptions/errors. We will have to also review the Exception handling flow with her later in the engagement. 5. [arpita@i2sbs.com] Marilza indicated that the SID-to-SLT-specific data mappings and the actual backend calls OSS/BSS should be built separately as access services. This effectively means that the IIB services built so far have to be divided into two parts – a mapping service and an actual backend call service. Marilza indicated that the services we've developed thus far in the ESB are "Access Services" or "Adapters" for Billing and Provisioning system operations. She also mentioned the importance of understanding the re-usability of these Access Services by different Business Services that would be exposed to BPM. She indicated that building of Business Services as composite services that combines a set of Access Services should be a design time task. Further discussion on these design points will be carried out when we go through the best practice design approach using "Extended Modification" process flow. 6. [arpita@i2sbs.com] The data usage is as per Scott’s advice (as attached with this mail). Later in the evening, Shirley showed the BPM Telecom Pack assets that were used from the PD. It was understood that we have not installed BPM Telecom Pack in the Process Center development server, however are using some of the assets in the PD only. We have the BPM Telecom Pack v7.5.0.0 and Marilza indicated that it is important to download and iFix without which this version of BPM Telecom Pack will not work with PD 8.5.5. Shirley was requested to open a PMR and get the iFix downloaded. Marilza indicated that she wants to know from where we got the XML schema files for data mapping as the Customer Order message available in BPM Telecom Pack was different in structure to what we've generated as part of our mapping. 7. Marilza indicated the importance of doing house-keeping tasks on the Process Center in order to clean-up the old snapshots. She indicated that she will point us to scripts that would help us to do this. Without such house-keeping, it is normal for us to observe degraded performance over time with PD and PC. By copy Arpita, If there are any specific recommendations given by Marilza during the review of the flows during my absence, please add those, tks.
21 | Prasad Shared the Best preactice and presetation received from Marliza | 2015-03-30 | Prasad Shared the Best preactice and presetation received from Marliza | Fwd: Process Designer Best Practices + CP two slides | Dear SOA Project Team, Please find below two slide decks requested from Marilza during the last day of the engagement. BPM best practices outline what we need to do to obtain optimal performance of the BPM development and production environments. MAC-D service identification slides were discussed when Marilza described the need to have MAC-D (Mode-Add-Change-Delete) processes different all the way from the top, tks. ---------- Forwarded message ---------- From: Marilza Maia <mmaia@us.ibm.com> Date: Mon, Mar 30, 2015 at 9:07 AM Subject: Process Designer Best Practices + CP two slides To: Prasad Kularatne <prasad@n-able.biz> (See attached file: BPM Best Practices.pptx) (See attached file: MACD Service Identification.ppt) PS: I'll send you the "Finds and recommendation document" by end of day tomorrow, Monday. Cheers, Marilza Maia IBM Sr. Certified IT Specialist IBM Software Group - Industry Solution Services San Francisco, CA mmaia@us.ibm.com 510-654-1858 Mobile Office
22 | Prasad reply to krishna emal | 2015-03-30 | Prasad reply to krishna emal | Re: FW: IBM Consulting for SLT SOA/BPM project - Day5 | Hi Krishna, Kindly note that the IBM Telecom Pack usage is a contractual obligation to SLT. i2S has contracted with N-able the use of IBM Telecom Pack in the Service Identification/Design phase and Build and Test phase. Only time we've used it is in SID data mapping and there too we've used an old telecom pack version and as Marilza pointed out our SID data mapping is incorrect and incomplete. Does it mean that we are to continue with that incomplete mapping? We as N-able will have a challenge in representing a solution to SLT that is not inline with IBM best practices. This is a serious concern and we will have to discuss this with IBM intervention, tks.
23 | Ajith shared comments on TC | 2015-03-31 | Ajith shared comments on TC | Re: IBM Consulting for SLT SOA/BPM project - Day5 | Hi Prasad, This project was proposed in December 2013 and contracted in August 2014, the version of the products would continue to change in future. We are not obliged to use future versions, but what is available at the time of our requirement and design. The version we used was the latest when we started and the file was obtained from IBM Passport advantage website, so that was the IBM released version for their customers. There could be another versions of the software just before we go live, that doesn’t mean we go back to the Requirement and design to re-do all our job in the new version. This is how software projects are executed, and we always baseline the software at the time of starting our requirements and installations. For new versions we shall provide migration path and we phase the implementations in future. It is good that we have a new release now and Marilza has done a great job in explaining the same to the project team, so we are planning to develop one end to end process and related services using this new version of the asset. As informed by Krishna we shall work with Marilza and the team to design and develop that process. Based on the outcome of the development of the identified process, we shall decide how to apply the same for the rest of the processes and services as needed. As re-iterated multiple times before Prasad, this project Solution is contracted by I2S to N-able and SLT. We shall take the recommendations from IBM as deemed required and apply it diligently. We have done this in the past and we have worked with IBM team effectively. As the Architect of this project I shall review the solutions with the team and advice the team the actions that they need to take. We have a contracted scope, timelines , cost and effort for this project and as a project team we shall manage it. Krishna, Please provide the details of the process we would like to work with Marilza , and schedule a call between technical resources and Marilza for planning and implementing the same. Thank you Regards, Ajith Kumar Knowesis Pte Ltd 100C Pasir Panjang Road #04-03 See Hoy Chan Hub Singapore 118519 Dubai (+971) 52 860 9501 Qatar (+974) 3304 5943 ajith@knowesis.com @ajithk From: Prasad Kularatne <prasad@n-able.biz> Date: Tuesday, 31 March 2015 3:25 am To: Krishnaraju <krishnaraju@i2sbs.com> Cc: Marilza Maia <mmaia@us.ibm.com>, Scott Glen <scott.glen@uk.ibm.com>, Can P Boyacigiller <can@us.ibm.com>, Dishagi Ratnapriya <dishagi@n-able.biz>, Suneth Kariyawasam <suneth@n-able.biz>, Shirley Nanayakkara <Shirley@n-able.biz>, Sujith Unnikrishnan <sujith@i2sbs.com>, Arpita Roy <arpita@i2sbs.com>, Ajith Kumar <ajith@knowesis.com>, Amila Hendahewa <amila@n-able.biz> Subject: Re: FW: IBM Consulting for SLT SOA/BPM project - Day5 Hi Krishna, Kindly note that the IBM Telecom Pack usage is a contractual obligation to SLT. i2S has contracted with N-able the use of IBM Telecom Pack in the Service Identification/Design phase and Build and Test phase. Only time we've used it is in SID data mapping and there too we've used an old telecom pack version and as Marilza pointed out our SID data mapping is incorrect and incomplete. Does it mean that we are to continue with that incomplete mapping? We as N-able will have a challenge in representing a solution to SLT that is not inline with IBM best practices. This is a serious concern and we will have to discuss this with IBM intervention, tks. On Mon, Mar 30, 2015 at 6:18 PM, <krishnaraju@i2sbs.com> wrote: Dear Prasad, I am resending this email, since it bounced back to my email address. Thanks & Regards, Krishnaraju Manjrabad Rathnakar. i2s Business Solutions India Pvt Ltd. Mobile: +91 9916035487 Skype: krishnaraju12 From:krishnaraju@i2sbs.com [mailto:krishnaraju@i2sbs.com] Sent: Monday, March 30, 2015 5:50 PM To: 'Prasad Kularatne ' Cc: 'arpita@i2sbs.com'; 'Amila Hendahewa'; 'Shirley Nanayakkara'; Marilza Maia; Can P Boyacigiller; Ajith Kumar; Scott Glen; 'Dishagi Ratnapriya'; Sujith Unnikrishnan; suneth@n-able.biz Subject: RE: IBM Consulting for SLT SOA/BPM project - Day5 Dear Prasad, Thanks for summarizing Marilza’s recommendations. We also agree that to accelerate the development, development assets from TP would be really helpful. We had an internal discussion with Ajith (Project Architect) on how to accommodate the recommendations and here are the conclusions as mentioned below: 1. We can take approach by developing the Extended Modification Process end to end using TP assets which requires IBM experts (like Marilza) to work closely with Shirley and Suneth (who has considerable understanding and comfort in using TP) . This would help us determine the effort utilization in completing the process. Based on the outcome of this, we can take up the similar strategy for the remaining processes. 2. In the meantime, without impacting the planned delivery of the processes which are already close to 70-80% completion, the remaining developers can continue working as scheduled. We need to prioritize the dependent sub process, so that End to End process will not be delayed. 3. The process models have already been closed after final review with the customer and, hence, we will not revisit those models. 4. The use case is already been defined in a approach in agreement with customer by using BWL for capturing detailed requirements “As-IS“ and “To Be” process models as a collaboration tools for creating and reviewing the process models for core and extended products. Thanks & Regards, Krishnaraju Manjrabad Rathnakar. i2s Business Solutions India Pvt Ltd. Mobile: +91 9916035487 Skype: krishnaraju12 From: Prasad Kularatne [mailto:prasad@n-able.biz] Sent: Sunday, March 29, 2015 6:51 PM To: Arpita Roy Cc: Amila Hendahewa; Suneth Kariyawasam; Shirley Nanayakkara; Marilza Maia; Can P Boyacigiller; Ajith Kumar; Scott Glen; Dishagi Ratnapriya; Krishnaraju; Sujith Subject: Re: IBM Consulting for SLT SOA/BPM project - Day5 Hi Arpita, Now that you are clearly aware of the recommendations for the implementation, I suggest you discuss with Project Architect and Scott as needed along with Marilza and take it forward in the future implementation tasks. Few things that Marilza strongly suggested need to be looked into if we are to be successful and timely in this project, 1. Data mapping must be redone (we've used old Telecom Pack assets resulting in a mapping exercise with large number of SID extensions, Marilza explained that our mapping is incomplete and potentially incorrect) 2. Process models are sufficiently detailed enough for developers to carry out development 3. Process models should be sufficiently different for MAC-D scenarios all the way from the parent flows 4. Process flow decisions needs to be externalized 5. Use-cases needs to be documented From my layman understanding these are very strong suggestions. If we do not strongly consider these now and adjust our implementation methodology accordingly, we may encounter significant delays later. On Sun, Mar 29, 2015 at 2:14 PM, <arpita@i2sbs.com> wrote: Hi, Please find some updates inline. Warm Regards, Arpita Roy Practice Lead (WebSphere Technologies) i2s Business Solutions India Pvt Ltd No:3421, 10th Main 3rd cross, 100 Feet Road, Indira Nagar II stage, Bangalore –560038. Mobile: +91-9008555443 (India), +94-765248219 (Sri Lanka) www.i2sbs.com From: Prasad Kularatne [mailto:prasad@n-able.biz] Sent: Sunday, March 29, 2015 1:41 PM To: Arpita Roy Cc: Amila Hendahewa; Suneth Kariyawasam; Shirley Nanayakkara; Marilza Maia; Can P Boyacigiller; Ajith Kumar; Scott Glen; Dishagi Ratnapriya; Krishnaraju Subject: Re: IBM Consulting for SLT SOA/BPM project - Day5 Hi all, With Marilza's concerns on the process flows we developed and the level of detail present in the models given to the developers, we wanted her to address these concerns by walking us through the flow as this has a significant bearing on the future activities of the project and the speed at which we complete the development tasks. 1, Process flow review: As per the request made in the day-4 session, Marilza went a little deeper into the process flows we've modeled. Marilza highlighted her concerns. a) [arpita@i2sbs.com] The first thing which Marilza pointed out and which the technical team also feels is that having different architects (initially Scott, then Andrew, then Marilza) frequently to review and recommend changes when each architect has his or her unique outlook may create conflicts and confusion for the team and add a lot of rework. Also any changes suggested cannot be implemented directly without consulting the project architect. b) Major concern was that MAC-D (Move, Add, Change and Delete) processes were exactly the same at the parent process flow level. Even at sub-flow level they appeared to be same and even the API called identified for each sub-flow was exactly the same across Create and Delete flows (we've documented all API calls for all MAC-D scenarios). Difference in logic could be identified deeper down in the flow only. c) Marilza highlighted the importance of the need to make these process flows different from the top most level. She strongly indicated this need as our process flows have to be self-descriptive. She showed a presentation from Can-Paul which indicated the level of re-usability that is typically present in MAC-D processes. She showed that each such process is different even from the top level. Arpita first felt that what she has done is in line with Scott's recommendations, however, she agreed the need to have the MAC-D process differences identified all the way from the top level. She agreed to work on this. [arpita@i2sbs.com] I understood Marilza’s recommendations. However, I did not immediately commit on making the changes. What I agreed upon is renaming some of the sub-processes for clearer understanding of an external reviewer who wasn’t previously involved in the project. For most other points (as highlighted in the previous mail) that since these are recommendations for implementation, we need to have a discussion with the technical team and especially the project architect and only after that decide which way to proceed depending on the real acceleration the new approach can provide. Also we may have to check with Scott on a couple of things in this regard. d) Marilza indicated the need to externalize decisions into ODM. There was a discussion on when and how to externalize the decisions and the importance of doing it to improve business agility. In our process flows we have not identified those decisions which should be externalized. Marilza indicated that it should be done by the BA (Arpita) with the direction of the Solution Architect (Ajith). e) Marilza also highlighted the need to have more details in our process flows that will be given to developers to avoid the room for developers to think on their own those that should be finalized at the BA level. She indicated that those flows have to be drilled down all the way to eTOM level-5 as much as possible. We need little more guidance as to how Arpita can effect this in the flows already done. [arpita@i2sbs.com] There is not a proper eTOM level 5. What Marilza meant was to drill the process models down to the API level everywhere. f) She also highlighted the importance of documenting use-cases in a self-descriptive format. She indicated the importance of doing this as the test-cases would be derived on this. SOA team felt the importance of getting an agreement on the use-cases for each MAC-D we are to implement without which it would be difficult to agree on the test-cases. Marilza showed a properly documented use-cases for MAC-D processes. [arpita@i2sbs.com] Again, since these are recommendations for implementation, we need to have a discussion with the technical team and especially the project architect and only after that decide which way to proceed. Also we may have to check with Scott on a couple of things in this regard. g) Marilza indicated the need to have a Master test plan including testing of services, unit testing of sub-flows, integration testing etc. [arpita@i2sbs.com] This wasn’t discussed with me. However, I would imagine that the SOA team who discussed this point must have informed Marilza that the test strategy and test plan are already under progress by the test team. 2. Meeting with Oracle Consulting Services: At our request, SLT arranged this meeting to help us understand how Oracle Consulting Services (OCS) plan to implement Siebel CRM in respect or Order handling and their expectation from the SOA layer. As part of our scope, we are expected to externalize any enrichment required to the SO so that it is in an acceptable format to the SLT Provisioning system. Our plan had b een to use an external mock-up service for this enrichment as there is no catalog existing at the moment. Marilza's indicated that we should build a process flow in a manner that there will be no change once the catalog for order decomposition is introduced. This is what we have communicated to SLT as well. The discussion focused largely on the use of catalog and how decomposition in different layers will be achieved. Following points were discussed; a) As per the finalized scope, OCS will not be implementing PH4C (Oracle Product Hub for Communications) in the initial phase. Siebel CRM will be Customer Master and will use its internal catalog for Commercial Product decomposition. Their internal catalog will not store any technical details of the order. This means that another external catalog is required to maintain the details of technical decomposition giving rise to the need for two catalogs referencing product data and two sets of details associated with such data. [arpita@i2sbs.com] SLT team insisted that PH4C Product Catalog must be implemented during the first phase and Oracle team said that they will internally discuss with their architect and other experts and come back on this. b) Marilza strongly argued the need to have one catalog to store details of Commercial to CFS, CFS to RFS and even logical to physical resources (however today logical to physical resource mapping is handled inside their provisioning system). She explained why this is needed and SLT thinking was inline with her explanation. Basically she strongly highlighted the unnecessary burden of catalog synchronization for order decomposition if two catalogs are to be maintained. c) OCS did not have an answer as to how they should handle the order process with a single catalog which will be queried by Siebel for commercial to CFS order decomposition by the CRM and CFS to RFS by the Order handling code. SLT highlighted absence of this information means that Siebel will not be able to complete the order processing with their vision of a single catalog. Therefore the discussion got concluded with OCS informing us that they will come up with their strategy to address a single catalog vision of SLT. 3. BPM performance analysis and housekeeping tasks: Marilza demonstrated the key housekeeping tasks that we should carry out on an ongoing basis, either through scheduling or manually by an administrator. She also indicated the pre-built scripts that comes with BPM that should be used. She indicated that the performance of the process center can be sizeably improved by routinely carrying out these tasks. She also highlighted the architecture of the 3-cluster Golden topology recommended by Scott which we must implement for the production environment during IBM BPM implementation. We also requested Marilza to share with the SOA team the content pertaining to important concepts she explained throughout the session, tks. On Sat, Mar 28, 2015 at 7:04 AM, Prasad Kularatne <prasad@n-able.biz> wrote: Hi all, Today's session was intended at walking the team through the SID data mapping exercise. We understood the importance of doing this exercise with the BSS vendor as the data mapping requires a deeper understanding of the the fields/elements for each back-end operation we will be using within our scope. I thought it was a very effective day for the team as they could really see the real acceleration provided by Telecom Pack. By copy Arpita, please update, add any points I might have missed. 1. Telecom Pack version: Importance of correct up-to-date Telecom Pack version was highlighted. Since we had used an older version of telecom pack, the data mapping we've already done in incomplete and the exercise should be carried out again. Marilza recommended us to use Telecom Pack v7.5.0.0 with iFix JR51530 Note: At this point, I feel that we should involve BSS vendor in this exercise and since we have to carry out the data mapping activity again, my suggestion is that we go ahead with the latest BSS system API's, this will allow us to get more support from the vendor which we is lacking at the moment. 2. SID data mapping exercise: Marilza demonstrated how SID data mapping exercise should be carried out with the use of Telecom Pack assets. It was basically a top-down approach. Once our implementable flows are finalized, we can map API calls invoked at each task to the TAM operations defined in Telecom Pack. Marilza also explained how the data mapping can be carried out and the need to update the extensions in the SID objects inside PD. Once this exercise is carried out, we can import the TAM operation into IIB which in tern will create the appropriate Integration Service. Once the Integration service is created in IIB, we can build the message flows to do the native-to-SID transformations. Suneth felt this methodology can potentially accelerate the data mapping exercise at least 2-3 times compared to the approach he took initially. 3. Process flow design review: Marilza indicated that importance of having separate process flows from ground up for Move, Add, Change, Delete (MAC-D) scenarios as each such business process is different. She also mentioned that when we model such process flows they should be sufficiently generic to handle orders for different types of products. Arpita agreed to get her expert advice on improving the flows. 5. Involvement of the Solution Architect: Marilza indicated that it would be important for Solution Architect to involve more in the design and development to drive the architectural decisions. More involved decisions relating to externalizing of decisions within process flow into ODM and determination of composite vs. atomic services were some of the areas Marilza thinks the Solution Architects involvement is required. 6. Level of detail required in Process Flows: Marilza's review indicated that the process models when passed on to the developers from the BA would required to be at a more detailed level. She suggested to always look into breaking the processes all the way down to eTOM level-5 as much as possible. More details on the input/output messages points at which we externalized decisions into ODM and detailed contextual documentation were recommended to be included in the process models once they are broken down into much more details level where possible. 7. Developers role: Marilza highlighted the importance of developers role in BPM development. They should question the BA and architect to drill down and understand the process flow better before starting their development. Thanks. On Wed, Mar 25, 2015 at 7:34 AM, <arpita@i2sbs.com> wrote: Hi all, Please find the updates on some of the points inline. Warm Regards, Arpita Roy Practice Lead (WebSphere Technologies) i2s Business Solutions India Pvt Ltd No:3421, 10th Main 3rd cross, 100 Feet Road, Indira Nagar II stage, Bangalore –560038. Mobile: +91-9008555443(India), +94-765248219 (Sri Lanka) www.i2sbs.com From: Prasad Kularatne [mailto:prasad@n-able.biz] Sent: Wednesday, March 25, 2015 3:32 AM To: Arpita Roy Cc: Amila Hendahewa; Suneth Kariyawasam; Shirley Nanayakkara; Marilza Maia; Can P Boyacigiller; Ajith Kumar; Scott Glen; Dishagi Ratnapriya; Krishnaraju Subject: Re: IBM Consulting for SLT SOA/BPM project - Day2 Hi all, Today's session started off with the installation of Telecom Pack assets on an SOA team members laptop to be used in the remaining part of the consulting engagement. By copy Arpita, please update, add any points I might have missed. 1. Marilza demonstrated how to resolve the dependency conflicts that arose when we started installing all the toolkits that comes with Telecom Pack 7.5.0.0 iFix JR48588. Finally we managed to have this version of telecom pack assets loaded into Shirley's laptop into a Process Center environment at N-able. 2. [arpita@i2sbs.com] We used one of smaller sub-processes “Track Service Provisioning Activity” inside the “Track & Manage Orders” sub-process from the “Extended Modifications” flow. This sub-process has one callback (which Marilza considers as a notification), 2 notification tasks and only one activity (Manage Customer Billing) which has 4 API calls to backend billing system. We used "Extended Modification" flow to understand the use of Telecom pack and how it will help us to accelerate our development. We used "Manage Customer Billing" activity within the process flow and started modeling it using Telecom Pack assets. 3. [arpita@i2sbs.com] We did not map our operations to TAM Applications and Operations, rather we only found from the Telco Pack Service Model (an excel sheet which comes with the ifix) the appropriate Telco Pack operation corresponding to our operation so that we can find the input and output of these operations. Currently, in the TP service model related resource interfaces (which contain these operations) are clubbed together and mapped to a particular TAM application. Using "Manage Customer Billing" as an example, Marilza demonstrated how to use BPM Telecom Pack. She demonstrated the need to understand the TAM Service Interfaces that contain "TAM Operations" we execute against the target systems within the activity. Within the above activity, we modeled a sub-flow and we found four operations to be executed against the BSS system and started mapping those to TAM Operations. She demonstrated how to import such operations in PD from the appropriate Telecom Pack toolkit and how we get the input and output message structures automatically in PD. 4. [arpita@i2sbs.com] Suneth/Shirley highlighted how when this exercise was being done originally they could not complete the allocated tasks (to get the descriptions of all the elements in the requests and responses of the API operations) because when they spoke to the SLT team they were unaware of the descriptions of the elements. Prasad suggested that we take up this work again with the BSS vendor to see if they know the appropriate descriptions. Once the Operations were mapped, we started the exercise of data mapping. As a preparation for that all relevant operations and elements of those operations were imported into an Excel sheet. During this exercise, we found certain elements in the SLT BSS operations were very specific to SLT BSS system and there was inadequate documentation (only Java doc) available to understand the use of these elements. Suneth/Shirley felt the need to work with BSS vendor team during the data mapping exercise to have a better understanding of these elements and therefore carry out the correct mapping into the SID data model. 5. There was a concern by the SOA team that during the data mapping, there were lots of elements that we could not map to a corresponding SID element and we therefore treated them as extensions. Marilza found out that we were using specific toolkits from a version of Telecom pack older than the one comes with iFix JR48588, and the organization of the Business Objects in that version was different to the one that comes with iFix JR48588. Taking "Customer Order" business object, she showed how different the organization of elements in the older version we were using and the one that comes with JR48588. This may be one of the reasons SOA team data mapping exercise resulted in a significant number of SID extensions. With the JR48588 toolkits, due to the hierarchical organization of related business objects, the mapping exercise would have been much easier and the team could have found the relevant entities easier. 6. Marilza indicated that she will get the latest recommended iFix version for the use in this project. On the third day we expect Marilza to help us in SID data mapping exercise and now that we have Operations from SLT BSS system with their elements and the relevant SID entities in Excel format, we can start the mapping activity from the morning with i2S team also connected via WebEx. We also plan to meet SLT, the Siebel project team, to understand how the order handling will happen with the new CRM implementation. The objective of this discussion is to understand how we should carry out order decomposition and issuing the RFS order to SLT OSS system. Currently what we've agreed with SLT was that we will use an external Stub Service to do the mapping (we will hard-code the required CFS to RFS mapping) however, we have not started analysis of their service order messages going to OSS or BSS yet. [arpita@i2sbs.com] Again, we are not going to do any mapping from CFS to RFS in the stub service. The stub service will have the hard-coded decomposition for each products(not CFS). Practically, because this will be a hard-coded response, it will be exactly for a given products, irrespective of what CFS are being passed.
24 | Marliza reply on Ajith email | 2015-03-31 | Marliza reply on Ajith email | Re: IBM Consulting for SLT SOA/BPM project - Day5 | Hello Ajith, the issue is NOT that you are using an old version of the Telco Pack (TP) but that it seems to me that the TP information model was not used correctly. It was assumed that all the order attributes existed in the Customer Order BO, however, there was also a Service BO and a Resource BO that was not used. It seems to me that the attributes already defined in the Service and Resource BOs were defined as extensions to the Customer Order BO and that's what needs to be fixed. That was my conclusion why there were so many attributes missing in the Customer Order BO. Furthermore, there might be other BOs that were not properly used. I think this is a good opportunity to get some TP skills transfer, update the code, and upgrade the TP. You don't necessarily have to migrate to the latest version of the TP, but you need to fix your flows to use the correct BOs, reducing the number of extended attributes in the Customer Order BO. Now, if you need to change the work you've done anyway, then I'd recommend to upgrade the TP to the latest version. It's your and Prasad's decision to upgrade the TP or not. I just think it might save you time in the end. iFIX JR51530 has been generally available since October 2014. Hope it helps. Cheers, Marilza Maia IBM Sr. Certified IT Specialist IBM Software Group - Industry Solution Services San Francisco, CA mmaia@us.ibm.com 510-654-1858 Mobile Office
25 | Ajith reply to Prasad Email | 2015-03-31 | Ajith reply to Prasad Email | Re: IBM Consulting for SLT SOA/BPM project - Day5 | Hi Prasad, As explained in the earlier mail, we have already started the process to use the new Telco pack for the selected process and services and based on the outcome we shall apply the same for other services. Just to correct you there are no incorrect mappings, the mappings are always customised based on the Source and Target. Telco pack provides fields for one end of the mapping , you still need to map that to the actual BSS and OSS fields. The suggestion from Marilza is to use out of the box fields in the new version , rather than using custom attributes along with the old data modal. Both options are viable technical options for the end to end service to function, and it is purely implementation decision. The new version has more out of the box fields, so we need less customisation which is good. Technical team shall discuss internally and we would take the decisions accordingly. Thank you Regards, Ajith Kumar Knowesis Pte Ltd 100C Pasir Panjang Road #04-03 See Hoy Chan Hub Singapore 118519 Dubai (+971) 52 860 9501 Qatar (+974) 3304 5943 ajith@knowesis.com @ajithk From: Prasad Kularatne <prasad@n-able.biz> Date: Tuesday, 31 March 2015 1:32 pm To: Ajith Kumar <ajith@knowesis.com> Cc: Can P Boyacigiller <can@us.ibm.com>, Marilza Maia <mmaia@us.ibm.com>, Sujith Unnikrishnan <sujith@i2sbs.com>, Suneth Kariyawasam <suneth@n-able.biz>, Arpita Roy <arpita@i2sbs.com>, Shirley Nanayakkara <Shirley@n-able.biz>, Dishagi Ratnapriya <dishagi@n-able.biz>, Amila Hendahewa <amila@n-able.biz>, Scott Glen <scott.glen@uk.ibm.com>, Krishnaraju <krishnaraju@i2sbs.com>, Sri Rajalingam <sri@knowesis.com> Subject: Re: IBM Consulting for SLT SOA/BPM project - Day5 Hi Ajith, Thanks for your mail. Small correction. On the first day of the SLT to-be architecture session in November 2014, Andrew recommended the use of Telecom Pack 7.5.0.0 with iFix JR48588, Subsequently Arpita has downloaded it. But for some unfortunate reason we've not used it. If we had used this iFix version we would have not run into an incomplete data mapping issue. We started using Telecom pack assets in January, 2015, by that time the latest version was JR51530 which was what Scott indicated as he was using when Arpita queried him. Now this is past. We've unfortunately used a 2011 version of Telecom pack that has resulted in an incomplete and potentially incorrect SID data mapping. My biggest worry is that, as Krishna has indicated, if we continue with the development without correcting this when we present it to the customer, he is unlikely to accept it. Effecting the correction now is better than getting exposed to customer and reworking later. Further we've not done operations mapping at all. Hence our solution will not have the desired decoupling at the process layer in line with TMF. Now we have the time to move in the correct direction. Hence as the project architect what we would request you is to lead this move in the correct path, tks.
26 | Prasad reply on Ajith email | 2015-03-31 | Prasad reply on Ajith email | Re: IBM Consulting for SLT SOA/BPM project - Day5 | Thanks Ajith. I think you have not quite understood Marilza's statement of incorrect usage of TP information model. 1. The data mapping that was carried out by the team was bottom-up. They started from BSS and OSS BO's and mapped the respective attributes to those attributes of the corresponding BO in the telecom pack. 2. Since Arpita was new to SID data mapping (as she indicated in the last week session), there were no specific guidelines given to the team in your absence - team was requested to do bottom-up mapping and not to use the mapping of operations. Hence there was no reference nor a structured way in which they could have mapped the attributes. 3. The issue with respect to Customer Order BO mapping was that they thought all the attributes of BSS/OSS Customer Order BO could be mapped entirely to Customer Order BO in the TP. However, this was not the case, from what I understand, in the old version of TP. Some attributes for this mapping were in Service Order and Resource Order BO's. Hence the team has missed mapping those and Marilza found out that this has caused extending of the SID data model when it should not be. 4. In the new TP version, we found this mapping is quite easy, as the organization of the attributes of Customer Order BO was more consolidated, and the team could have done the mapping exercise more efficiently and more completely. When the mapping exercise is not complete, the value of the use of SID model as a common information model in our project goes down. Arpita witnessed this in the session last week. She may be able to explain this more technically than I can. When the team was requested to do bottom-up mapping (and specifically not to do operations mapping - see Arpita's instructions), they needed more guidance and a structured way. At least the mapping they have done could have been reviewed. Let's see with the new mentoring Marilza has given how we can carry this exercise more completely and efficiently.
27 | Prasad sent email to krishna | 2015-04-02 | Prasad sent email to krishna | Re: IBM Consulting for SLT SOA/BPM project - Day5 | Hi Krishna, Perhaps you may not know of the original contracting and agreed SOW. i2S committed to deliver project using Telecom Pack and the SOW clearly states that - your commercials are including this commitment. Since i2S does not have skills in Telecom Pack, what is reasonably expected is that you take action on bridging this gap as it is your contractual commitment. We intervened and brought a resource straight from Telecom Pack team in the US. It is our collective duty to use her advice. You need to know that we spent SLR 2.6M (US$ 20k) for her one week assignment! If you drill down and see how Arpita and the team has recommended the use of telecom pack and how they created their own toolkit from old telecom pack assets, it really is daunting! If we have gone in the wrong direction, there is no point in going in the same direction citing acceleration and timelines! Thanks.