## Sheet1
Activity | Date | Remarks
DEV environment | 2015-04-27 | By STE
DEV Installation Doc Review | 2015-04-28 | By STE, Hui, Kok Yuen
UAT Oracle installation | 2015-04-29 | By STE
UAT BPMS installation | 29 April PM – 30 April
Prod Installation Doc Review | 2015-05-04 | By STE, Hui, Kok Yuen
Prod Oracle installation | 4 May – 5 May | By STE
Prod BPMS installation | 2015-05-05
Acceptance Test Plan sign off | 2015-04-28 | NUS
DEV / QAT / PROD Up | 2015-05-08 | with SAP / Peoplesoft